AUV Gulper Update
1. Sampler:

a. Larry had lexan vapor polished, Ti springs made, and is trying to find the right size cylinder for the seal. Anticipate ROV testing within a week.
b. DI testing was not successful but we have identified the problem and will fix it. Have to schedule time to retest on AUV CTD run. NOTE: Hans thinks the AUV will go out next week.

2. Pin Puller:

a. Should receive 25 lb pin puller next week. We can we mount it for testing in our current housing. Hans thinks it will be easy to change the voltage of the pulse, thus we can use our current electronics in the AUV MVC to trigger a sample with the pin puller.
b. Began schematic for electronics, no progress on software

3. Ship Time

a. Will give back June days. Save July days for possible single sampler test.
b. Will try to schedule more days in Nov/Dec time range.
Gulper Test Plan

1. Test Sampler

a. DI test, repeat on AUV possibly next week, piggyback on AUV CTD.
2. Hold mechanical CDR (July)
a. Review foam pack, sampler bottles, pin puller housing, and mounting rack.

b. Order foam pack as soon as after the review as possible

3. Trigger Sampler on ROV- piggyback on other missions
i. Measure time to fill

ii. Compare salinity, nutrients with Niskin bottle and ROV CTD

4. Electrical/Software PDR (August)
5. Assemble mid-section (Sept/Oct)
6. Test system- 4 days in late fall, we already have ship time Nov 1, 2.

