AUV Gulper Fall 2006 schedule

1. Late October- 1st week of November

Pressure testing of node controller (Jim S. 1 day)


Assembly of actuator housings (Larry 2 days)


Pressure testing of actuators (Jim S. 1 day)


Potting of cables (Jim S. 0.5 days, Tom 1 day)

2. Nov 6, 7 

Zephyr Deployments

Goal: To test single sampler with pin puller actuator on RS485 bus from MVC

3. Nov-early Dec

Integrate foam pack, mounting rack and actuators into spare mid-body (Larry 4 
days)


Assemble samplers (Larry 4 days)


Test samplers (Alana)

4. Dec 4, 5


Goal: To test integrated 10 sampler system with prescribed sampling pattern

5. Dec 13, 14


Goal: To test integrated 10 sampler system with prescribed sampling pattern

Resources requested:
1. Machine shop time- the following parts still need to be machined for our December deployments
