AUV Gulper resources for Fall 06:

2006 Deployments:

Nov 6, 7
single sampler sample validation with solenoid actuation
Dec 4, 5
single sampler with new actuator, electronics, cabling and software 
Dec 13, 14
single sampler with new actuator, electronics, cabling and software
Task List

Mechanical

1. Machine Ti sampler parts

by mid-Dec
a. Machine shop
3 days



2. Assembly of actuator housings (12)
mid-Nov
a. ME tech 3 days


3. Assembly of trigger mechanism (12)  Dec/Jan
a. ME tech 3 days

4. Pressure test actuators


late Nov

a. ME tech 1 day

5. Pressure test electronics

late October
a. ME tech 0.5 days


6. Integrate foam pack, rack, and actuators in mid-body 
Jan
a. ME tech 5 days


Total 2006 ME tech
7.5 days
Total 2006 machine shop
3 days

Electrical

1. Build 12 node controller boards 
last week of Oct
a. EE tech 3 days



2. Wire actuator housings

late Nov

a. EE tech 2 days

3. Splice and mold cables

late Nov- Dec
a. EE tech 2 days

b. ME tech 1 day
Total 2006 EE tech 7 days

Total 2006 ME tech 1 day

System testing, tank testing, cold testing 
Jan

ME tech 5 days

