2007 Proposal Process – Internal-Only Projects

Submission Deadlines: Phase I – August 22nd, Phase II – September 28th 


	Project Number:
	900502


	Project Start: Jan. 1,
	2007
	Project Duration (in years):
	2


Please indicate what type of project is being proposed (mark only one).
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	Feasibility/Scoping

[Less than 100 days effort]
	Development

	Research
	Infrastructure1
	Education
	Time Series


Project Manager/PI:

Ken Smith


Project Title:

Benthic Rover
1) ABSTRACT (new projects only)
N/A

2) PROPOSAL
a) The problem addressed (new projects only)
Statement of the problem

N/A
b) Approach to the problem (new and continuing projects)
Status of project

Milestones achieved in 2006:
1. Frame, floatation, and propulsion system were built at Scripps and delivered to MBARI in February 2006.

2. Titanium housings were built and pressure tested.

3. Main vehicle controller and motor controllers were acquired, tested, and integrated on the vehicle.

4. All cables and connectors needed for 2006 were purchased.

5. The wiring chasis for the initial electronics and battery sphere was completed. Software scripts were written to control the Rover.
6. The proto-Rover, which consists of a working propulsion system, current meter, and acoustic modem/release, was built and tested in the test tank and cold room. 

7. The proto-Rover was deployed twice from the Point Lobos at Smooth Ridge (depth 980m) in July 2006. During these deployments, we tested the propulsion system, the acoustic communication, and the drop weight release. All of these systems are working successfully. 
8. We gathered accelerometer data which provided useful information about the Rover in free fall and the impact of hitting the sea floor.

9. We will be testing the proto-Rover to depths of approximately 4000m at Station M in August 2006 during Ken Smith’s Atlantis cruise.

We plan to accomplish the following tasks by the end of 2006:

1. Hold Critical design review
2. Complete design and fabrication of respirometer racks

3. Short autonomous deployments in late fall 2006

4. Collection of first science data with Rover

5. Lab testing and evaluation of ultrasound transducer array

Results to date

1. Successful test tank deployments 

2. Successful development and deployment of basic Rover platform.
3. Engineering data which characterizes Rover dynamics

4. Presented design results at ASLO 2006
Publications (from the last 5 years)
Insert Hawaii ASLO poster
Smith, K.L., Jr., R.C. Glatts, F. Uhlman, A. Tengberg, R.J. Baldwin, R.N. Glud, P.O.J. Hall, G. Holst and B. Grunwald. High resolution acoustic and optic measurements of deep-sea sediments : in situ monitoring to 4100 m depth. Deep-Sea Res. (in prep). 

Smith, K.L., Jr., R.S. Kaufmann, R.J. Baldwin and A.F. Carlucci (2001) Pelagic-benthic coupling in the abyssal eastern North Pacific: an eight-year time-series study of food supply and demand. Limnol. Oceanogr. 46: 543-556. 

Smith, K.L. Jr. and R.S. Kaufmann (1999) Long-term discrepancy between food supply and demand in the deep Eastern North Pacific. Science 284: 1174-1177. 

Smith, K.L., Jr., R.C. Glatts, R.J. Baldwin, A.H. Uhlman, R.C. Horn, C.E. Reimers and S.E. Beaulieu (1997) An autonomous bottom-transecting vehicle for making long time-series measurements of sediment community oxygen consumption to abyssal depths. Limnol. Oceanogr. 42: 1601-1612. 

Plans for 2007
Since building an autonomous vehicle capable of 6-month operations is a challenging task, we are developing the Rover in stages. We will start with a vehicle capable of short term or tethered deployments. The tethered vehicle will take advantage of the available power and communications at the MARS node. This will allow us to work simultaneously on developing some of the capabilities required for autonomous operation while the vehicle is out in the field collecting data.

If the MARS node is not an available resource in 2007 our contingency plan is to do longer autonomous deployments.
Engineering/technology development

1. Complete design and fabrication of scanner
2. Purchase and integrate transit camera and video controller

3. Build, test and deploy cable pack

4. Build and integrate load controllers for power switching, monitoring, and ground fault detection

5. Deploy Rover on MARS node for extended period, transmit respirometer and other instrument data as well as video to shore

6. Develop software for autonomy and fault recovery

7. Deploy Rover on autonomous mission

8. Engineering and Science publications

Field programs

   [Click here to enter text]   
Data (availability outside project team, uniqueness)
ROVER II provides an autonomous platform from which to conduct a diverse series of measurements at the deep-sea, sediment-water interface for extended periods of time, months to years. These measurements include sediment community oxygen consumption, sediment surface fluorescence, sediment structure, megafauna density and movements and bottom current flow. In addition, sensors from other investigators can be accommodated on the ROVER platform to increase the diversity of concurrent measurements of bottom water and sediment properties along a time-series, transect of stations.
Significant changes from previous project proposal (continuing projects only)
Since MARS will not be installed this year we plan to use our fall ship for short (1-2 weeks) autonomous deployments. During these deployments we will use alkaline battery packs to power the Rover. We hope to have a basic science instrument package mounted on the Rover.
c) Specific deliverables (new and continuing projects)

1. ROVER Scanner assembly

2. Operational tethered vehicle

3. Deployment of tethered vehicle on MARS node

4. Development of autonomous components (power management system)

d) Project team (new and continuing projects)
Ken Smith: principle investigator

Paul McGill: electrical engineer

Alana Sherman: electrical engineer

Doug Pargett: mechanical engineer

Rich Henthorn: software engineer, embedded system development

Andrew Chase: software engineer, user interface and data systems development

John Ferreira: mechanical technician

Larry Bird:  mechanical technician, cable pack management

e) Project lab space (new and continuing projects)

We would like to continue using our current lab space outside the cold room.

3) BUDGET JUSTIFICATION (new and continuing projects)
2007 Benthic Rover Budget:

[image: image1.emf]Instrument Qnty.Cost per unit

2007 Cost

Estimate

Rover Instruments

Current Meter 1 $7,535.00 $7,535.00

Video Camera-BR 1 $1,975.00 $1,975.00

Digital Camera 1 $15,000.00 $15,000.00

Strobe 1 $9,400.00 $9,400.00

Recovery Instruments $0.00

Burnwire releases 5 $350.00 $1,750.00

HomerPro 1 $4,800.00 $4,800.00

Acoustic modem 1 $10,769.64 $10,769.64

Controllers/Electronics

Custom electronics 2 $5,000.00 $10,000.00

Video server 1 $1,300.00 $1,300.00

Development software 1 $1,000.00 $1,000.00

Fluorometer 2 $4,000.00 $8,000.00

Motor controller 5 $500.00 $2,500.00

Misc. cmpt/hardware 1 $2,000.00 $2,000.00

Battery Packs 1 $2,000.00 $2,000.00

Mechanical System

Cables and Connectors 1 $20,000.00 $20,000.00

Scanner Assemblies 2 $6,300.00 $12,600.00

Adhesive 1 $400.00 $400.00

Misc mech parts 1 $5,000.00 $5,000.00

MARS deployment

Umbilical 1 $5,000.00 $5,000.00

Umb. Line drivers 1 $1,500.00 $1,500.00

MARS interface 1 $10,000.00 $10,000.00

General

Freight 1 $500.00 $500.00

Tools 1 $2,000.00 $2,000.00

Supplies- Eng. Lab 1 $3,000.00 $3,000.00

Supplies- General 1 $4,000.00 $4,000.00

Travel 1 $6,000.00 $6,000.00

Conference Fees 1 $1,800.00 $1,800.00

Total Budget $149,829.64


This budget assumes that the respirometers and rack will be completed by the end of 2006. The money earmarked for the MARS deployments will be used for Lithium battery packs if MARS is not ready and we need to make autonomous deployments instead.

4) MILESTONES (new and continuing projects)

	
	Milestone 1
	Milestone 2
	Milestone 3
	Milestone 4
	Milestone 5
	Total Resources
 for each resource category for all milestones listed here

	Milestone Date
	
	
	
	
	
	

	Milestone Description
	
	
	
	
	
	

	EE
	
	
	
	
	
	

	SE
	
	
	
	
	
	40 A.C.

	ME
	
	
	
	
	
	

	Support Engineering

	EE Tech
	
	
	
	
	
	

	SE Tech
	
	
	
	
	
	

	ME Tech
	
	
	
	
	
	

	Machine Shop
	
	
	
	
	
	


5) RISK MATRIX (development and infrastructure projects only)
Please carefully read Section 5.2.3 in the instructions for internal proposals for an explanation regarding the risk matrix. This table must be completed for ALL development and infrastructure proposals (new and continuing). The instructions can be found at http://mww.mbari.org/resources/2007_Proposal_Process/Internal-only_Instructions_2007.htm.
	
	Technical Risk
	Organizational Risk
	Tech Transfer Risk
	Labor Estimate Risk

	High
	
	
	
	X

	Medium
	X
	
	
	

	Low
	
	X
	X
	








� Development and infrastructure projects must complete the risk matrix (see item #5 at the end of the proposal form).


� This number should be the same number you entered on the resource requests for this particular resource.
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2007Budget

		Instrument		Qnty.		Cost per unit		2007
Cost
Estimate		Notes

		Rover 
Instruments

		Current Meter		1		$7,535.00		$7,535.00

		Video Camera-BR		1		$1,975.00		$1,975.00		Spare

		Digital Camera		1		$15,000.00		$15,000.00

		Strobe		1		$9,400.00		$9,400.00

		Recovery Instruments						$0.00

		Acoustic releases		2		$1,000.00		$2,000.00

		HomerPro		1		$4,800.00		$4,800.00

		subtotal								$40,710.00

		Controllers

		Controller and 
custom electronics		2		$5,000.00		$10,000.00

		Video server		2		$1,300.00		$2,600.00

		Development software		1		$1,000.00		$1,000.00

		Fluorometer		2		$4,000.00		$8,000.00

		Motor controller		1		$2,500.00		$2,500.00

		misc. cmpt/hardware		1		$2,000.00		$2,000.00

		sum								$26,100.00

		Mechanical System

		Cables and Connectors		1		$20,000.00		$20,000.00		come back and fix this

		Batteries		1		$2,000.00		$2,000.00		ken??

		Umbilical		1		$5,000.00		$5,000.00

		Umb. Line drivers		1		$1,500.00		$1,500.00

		MARS interface		1		$10,000.00		$10,000.00		Ask ODI, for batts if mars not ready

		Scanner Assemblies		2		$6,300.00		$12,600.00

		Adhesive		1		$400.00		$400.00

		Misc mech parts		1		$5,000.00		$5,000.00

		sum								$56,500.00

		General		1		$0.00		$0.00

		Freight		1		$500.00		$500.00

		Acoustic modem		1		$10,769.64		$10,769.64

		Tools		1		$2,000.00		$2,000.00

		Supplies- Eng. Lab		1		$3,000.00		$3,000.00

		Supplies- General		1		$4,000.00		$4,000.00

		sum								$20,269.64

		Travel		1		$6,000.00		$6,000.00		ken??

		conf fees		1		$1,800.00		$1,800.00

		Total Budget						$151,379.64





LaborBudget

		





Formatted budget

		Instrument		Qnty.		Cost per unit		2007 Cost
Estimate

		Rover Instruments

		Current Meter		1		$7,535.00		$7,535.00

		Video Camera-BR		1		$1,975.00		$1,975.00

		Digital Camera		1		$15,000.00		$15,000.00

		Strobe		1		$9,400.00		$9,400.00

		Recovery Instruments						$0.00

		Burnwire releases		5		$350.00		$1,750.00

		HomerPro		1		$4,800.00		$4,800.00

		Acoustic modem		1		$10,769.64		$10,769.64

		Controllers/Electronics

		Custom electronics		2		$5,000.00		$10,000.00

		Video server		1		$1,300.00		$1,300.00

		Development software		1		$1,000.00		$1,000.00

		Fluorometer		2		$4,000.00		$8,000.00

		Motor controller		5		$500.00		$2,500.00

		Misc. cmpt/hardware		1		$2,000.00		$2,000.00

		Battery Packs		1		$2,000.00		$2,000.00

		Mechanical System

		Cables and Connectors		1		$20,000.00		$20,000.00

		Scanner Assemblies		2		$6,300.00		$12,600.00

		Adhesive		1		$400.00		$400.00

		Misc mech parts		1		$5,000.00		$5,000.00

		MARS deployment

		Umbilical		1		$5,000.00		$5,000.00

		Umb. Line drivers		1		$1,500.00		$1,500.00

		MARS interface		1		$10,000.00		$10,000.00

		General

		Freight		1		$500.00		$500.00

		Tools		1		$2,000.00		$2,000.00

		Supplies- Eng. Lab		1		$3,000.00		$3,000.00

		Supplies- General		1		$4,000.00		$4,000.00

		Travel		1		$6,000.00		$6,000.00

		Conference Fees		1		$1,800.00		$1,800.00

		Total Budget						$149,829.64






