Benthic Rover Project Meeting 

16Nov06

Attending:

Paul McGill, Rich Henthorn, Andrew Chase, Brett Hobson, Alana Sherman, Ken Smith

Old items

1. What needs to be done next to get the respirometer and rack designs moving ahead?

a. Get a “rack simulator” for Rich so he can get started on the programming. Need lower limit switch mounted (Paul will talk to Jim S.)

b. Need to replace all the SS hardware on the Rover with Ti (Jim get list from Doug). – Jim has list, nothing ordered yet – not a priority for Dec, Paul will show Jim where our existing Ti hardware is.

c. Figure out what topside Acoustic Modem we’ll use in the future (e.g. Nov) (Brett) – We’ll use Han’s modem, and we’ll buy a MF xducer, cable, and filter. Everything is on order.
d. Need to order connectors, cables, and molding ASAP – Done, Seacon said they’ll ship this Friday, need to verify (Paul)

e. Need to make test cables for optode, rack motor, camera (Alana and Paul)

f. Still need to archive mission data from the Atlantis cruise (Andrew) – Rich has given Paul most of the data, but some are still missing

g. Western Flyer cruise has been delayed until Dec 11th thru 16th. Need to find out from Ken how many berths available and who should go. Preliminary list: Ken, Jake, Henry, Mike, Alana, Paul. Berths for 11.

2. What needs to be done in the near term?
a. Check the Acoustic Modem, which seems to be dead after return from Benthos (Brett and Paul) – still waiting for test cable; get from Hans?
3. What needs to be done this year?

a. Improve drop-weight mechanism – its too difficult to service at sea. – Jim is working on the jack, Frank has welded some pieces, awaiting reassembly, still need safety pin design – still not done.

4. Mechanical 

a. Most of the respirometers rack assemblies drawings are in the shop, Johnny is working from the SW model in other cases, rack is pretty much on schedule and should be working by the end of the month.

b. Build the respirometers – acrylic tubing is here, Ti knife is here, lids need to be made, but no acrylic sheet here yet. Brett has questions about the purge valves – need to build and test one.

c. Propulsion motors are remounted but one of the hose caps is leaking and so it needs replacement (Johnny)

5. Electrical

a. Need to test main batteries after tank tests to see if they can be deployed off Lobos in Dec. (Paul)

b. Need to check polarity of rack motor wiring (Alana).

c. The video cameras and Axis video server are here, tested, and working.

d. Do we need any blinky lights visible outside the MVC to indicate vehicle status?

e. Tom is working on the MVC sphere rewiring and it should be done this week.

f. Minirover is having problems, Paul will fix.

6. Software

a. Check that new current meter is code-compatible with old current meter (Rich). Need to set up new meter first (Paul).

b. Rich and Andrew have been doing state machine design for the main Rover program.

c. Rich can capture images from the video server.

d. Software readiness review will be held on Tue, Nov 28th. We should talk to Duane about this first (Rich, Andrew, Paul)

e. Need to test Parvus enet switch to make sure it requires no configuration (Rich and Alana).

7. Dive days:

a. We still have 2 Lobos days left in 2006. Dec 18th and 19th will be used for Rover

b. First dive days for Rover in 2007 are Feb 1 thru 7 on W. Flyer, but these dates will probably change to be earlier.

