MRS (Project # 900617)  Labor and Expense Summary

Shared resources:




Proposed

New
ME tasks:
mechanical layout




4d

4
ROV interface





2d

2


break-away hyd.




2d

0 (CO)
Parts purchasing




1d

0 (KR)
lab test






1d

1
re-work





1d

1
"depth capture, deck/lab incubation"


1d

1
Mechanical layout




10d

2 (MT)
re-test in lab





1d

1
prep and mob





0.5d

.5

Total





23.5

12.5
SE tasks:

modify BRS code




2d

0 (CO)
test






4d

0 (CO)
prep and mob





1d

0 (CO)
re-work





2d

0 (CO)
prep and mob





0.5d

0 (CO)
Midwater deployment




1d

0 (CO)


Total





10.5

0
EE tasks:

Electrical layout




2d

0 (CO)
lab test






1d

0 (CO)
re-work





1d

0 (CO)
re-test in lab





1d

0 (CO)



Total





5

0
Other Tasks: 

MT

Generate prints




10d

0
machine prints





5d

0
QC and assemble mechanicals


3d

3
assemble and install sensors



3d

3
wire up E-housing components


1d

1


Total





22d

7
ET

wire up processor/IO




4d

4
Wire up U/W cables




2d

2
wire up power/batteries



1d

1

wire up J-box





0

2


Total





7

9

Support Engineer

Electrical layout




1d

0 (done)
wire up E-housing components


1d

0 (ET)
lab test






1d

1
re-work





1d

1
prep and mob





1d

4
technician mananagement



0

4

testing and tweaking




0

4

Total





5

14

Machine Shop

PV






2d

0
Optode adaptors




3d

3
motor parts (3)





3d

3
QD assy





2d

2
MRS frame/misc




5d

10

Total





15

18
	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	


