Pelagic Benthic

March 13, 2013

- Hours on project

| Engineer | Hours allocated | Hours used | Hours for cruise | Remainder |
| --- | --- | --- | --- | --- |
| Alana | 500 | 186 | 100 | 214 |
| Paul | 240 | 81 | 100 | 59 |
| Rich | 350 | 28 | 100 | 222 |
| Brett | 100 | 30 | 0 | 70 |
| Larry | 200 | 100 |  | 100 |
| Johnny |  | 92 | 100 |  |

- Project Tasks

  - Pulse 62 General Prep

    - Figure out mounting of stereo cameras for Ricketts- Brett, talk to Conway about tool sled

  - Pulse 63 Schedule

    - Flyer shipyard until Feb 2014, talk to Etch - Ken

      - Will change rover sampling schedule to save power

  - Benthic Rover

    - Design and test Rover Sleepy board – Paul, Jose

    - Tom building up two optode assemblies

    - Make spare

      - deck cable – Alana

      - junction box, at Seacon being potted

    - Data backup –Rich

      - Come up with meaningful time estimate –Rich

        - Investigating what kind of change to the kernel

          - It will be a kernel mod

          - Evaluate non-USB options for storage –Rich NO Progress

    - Fluoro reference on bumper

      - Johnny will figure out how to mount

      - borrow black shroud from peter walz

    - Anodize spare chamber knife edge -Johnny

    - Wish list

      - better chamber camera

  - Time Lapse Camera

    - Determine FOV in test tank

      - Paul is comparing test images to calculations, in progress and good progress

      - Alana took invaluable measurements

    - Issue with Tattletale

      - going to bring out reset line

      - add relay to close reset to gnd

    - Use free weights for camera tripod

      - change release mechanism- Johnny in progress

      - reweight entire tripod

    - Adjust camera settings based on test tank images

    - Make 2 extension cables - Alana

    - Calculate power budget – in progress

    - Get current meter working –Paul in progress

    - Mount current meter –Johnny

    - Make short spar buoy –done except for beacons mounted

  - Stereo Camera systems

    - Fit it into tool sled – Brett and Johnny

    - Hard drives to store data – Rich ordered done

    - Email Dave Caress - Alana

  - SES

    - Motor leaking a bit of oil

      - Old motor refurbish – sent to McLane

    - Add feature to wakey such that it will remove power from stack if has been awake for more than X minutes –Paul, with Rich’s help

  - LSTs

    - Next ship day Thursday April 4

    - Build up shallow unit 2

      - Larry finished machining body

      - Larry working on sampling mechanism

    - Upgrade electronics to custom microprocessor board?

    - Fuel gauge, needs more investigation

      - look into Dallas part used by Chaffey –Paul

    - Actuator replacement of burnwires?

    - Test guillotine on Ventana, -Alana check schedule

  - Sediment traps

    - Fix clogging issues

    - New fiberglass sediment traps

      - they are being Teflon coated somewhere, Brett will check up on this

      - Need mounting holes compatible with frame - Johnny

      - need to talk to Conway about mounting it to elevator -  done

  - Other

    - Look at budget to see how much money we have left

      - looks better than I thought we are not broke

  - Weights

    - One weight for SES one for Rover

    - Rover weights need holes

    - In progress - Johnny