| 16 Dec 2015 |  |
| --- | --- |
| World according to Henry | Arctic proposal is in Megafauna in Rover chambers. Data files are UTC. File name is local time. Chambers with animals not always associated with high SCOC |
| Larissa | Data collection to start in Jan. 2 yr starting now |
| LST | Does Brent Jones want to LST antenna (Castroville). Ball in his court |
| To do | Current meter repairs after Jan 1 they will honor quote Order more re-enterable after cruise PAUL beacon spreadsheet is in inventory folder. SES has VHF but no satellite- get satellite FIND Color plate- got image from Kathy- still no reply from Kathy- Not in N. side cabinets of test tank Need to send in new drawings of battery schematics to allow correct connectors from factory- ALANA and PAUL- so much progress. Rover drawing is correct. Cam tripod controller and strobe connectors were wrong, so drawings have been updated with Electrochem. They are sending it back soon.Ask in Jan Current vs archive Make for Camera tripod and Rover Folders- PAUL, ALANA, RICH |
| Budget | Year end 2015 and early 2016 expenses- EVERYONE- send Crissy your wish list and cost estimates Beacon- SES. Could buy Argos beacon like we have on others ($4500- lasts>yr). There’s a smaller Argons (Lithium batts- $3125) . ibeacon issue has been resolved ($3-5K)? Argos. Stick with what we know. AS-900A beacon. Alana to order. Order spare seacon connector for new cable (LF modem) Weights for Johnny in Jan. |
| Pulse 66 Cruise debriefing | MF modems do not work. Will go over what we’ve changed PAUL- Tell them the problem and send them the cost of the dive. Talk with Brian re: Benthos to get a contact number. Dale Green no the right person. Write Joe Borden instead |
| Rover | Axis video receiver- is there a replacement? We can buy same (is obsolete) for $800. Newer model is available, but does not have a serial port. Otherwise should work ALANA’s inclination is to buy duplicate of what we have now. Alana to buy spare Axis. Buy spare pressure switch next year. PAUL to assess spares for beacon switches. Foam pack also has strobes that are OURS, we can reuse. Disk corruption issue. Recovered SCOC data 21-June-22 July. 14 files. ALANA to process. RICH ADD serial number to optode data files each line of cys log and csv files. Jpgs split into many pieces and so far can’t be reconstructed. Rich to try another method. Add data to project library and explain situation. Worth analysing and using mean insertion depth? Alana to assess slopes. Cameras spares: B&H- Do we have the money?? Going to buy a spare lens like the one the transit camera uses. Give Brett the one we borrowed. We don’t have a spare flat port for the prosilica housing (transit cam). Replacement optics. Have housing with chassis and power supply. Strobes: ALANA has a spare but there is a pressure cycling issue10K lantern shark? Needs testing. Alana made all cabling. Test in pressure tank. Remind in Feb. Assess all spares in Jan Check optode 801 and connector ALANA. Feb JOHNNY (2016 or once confirmed have $) buy more weights (bar). Buy 10ft. |
| Grab resp | Need to confirm on grabs, but looks like neither chamber optode worked. Both reference optodes seemed to work (clear tidal cycle). CRISSY. Are they in the same port? What’s the same on these? Plug each one into serial port (with power). Check both loggers to see what’s going on. Unplug optode and see if it’s sending a dummy number. Run optode sitting on bench. Take pics. Check SN of ones that worked before to verify is these have worked in the past (Henry here next week). CRISSY TOMORROW |
| SES | In future should put an argos on it TS 7250 we own two but they are not identical but they could be spares. Should RICH set up that spare? Yes. So will have spare processor, camera- just ordered. Rev A was first one but didn’t do what it says. Got new board Rev B. |
| New battery housing endcap-Alana and Johnny | Have all connectors, have to decide where to put them. Have connectors, proceed cheaply- too successful elsewhere |
| Snappy software-Rich | Alana- Needs to setup with camera, strobe, LEDs. The Rich will do the software. Hand over to Rich |
| LED lighting-Brett | Have arrived. Brett has used his set in AUV. They work in the tank but don’t know lighting specs. Charge cycle is similar to current strobes, but can be adjusted |
| Scanning contract-Crissy | They have all tripod film. QC, uploading, organizing. Camera sled in 2016 |
| Multibeam data | Talked with Kelly, preparing paper for DSR because not calibrated |
| Manuscripts | - SES paper- Fluorometer standard. On track to finish this by Nov? Table and reference objects. Paul re-writing intro to compare to Carbon flux explorer - PAUL to send CRISSY link of SES images. Crissy to annotate images in VARS and get surface area. Somewhere in Project library - Station M modelling- Kathy incorporating comments - Megafauna sizing- 2 reviews in, provisional acceptance |
| Camera tripod | Bathysnap- own housing? How to synchronize? Remote shutter, give it long exposure time. We don’t know if we can get another camera from her. Just use our system Test deploy it at MARS Think about options Get from Jen- specs of Bathysnap- height, type and angles of camera and strobe, type of camera, port, etc. Any spare parts we can use?? Test it in June (Carson dates). Alana Concern about old benthos film cam housing is whether we can align camera with port, based on diameter. End cap of housing does not come off. Slave camera so only use one strobe, remotely. No intelligence needed in second camera. Can’t use just light to trigger because it would require the camera to be on all the time. ISOLATE so if Bathysnap floods it’s not a problem. Revisit after 1st of year. Better to have both cameras the same. Wait and test |
| Winch | Brett owns it now |
| Deploy camera tripod in June | ALANA contact DMO |
| Personnel schedules | Paul and Johnny taking off as often as possible Alana- out of office May, June, July. Work from home Aug. Should be back in 3 days week starting Sept. |