	Aug 24, 2022 

	Laser measure
	Major breakthrough but not a solution yet. 3D space
They sort of line up. How to turn those into laser direction and offset vectors that Dan needs in calibration file?
Paul is poking his head up from a rabbit hole
Mount on Flyer before cruise. Bring target

	Loop and Cross
	Kent wasn’t able to do any loop and cross before tiny left Station M. Rover is progressing right speed and direction

	Macro system
	Next time out: October.

	Cruise
	More graham crackers
Cherries
Two t-shirts (Pulse Rover) and stickers
Box cores think about it
Leave all cages ashore. Just wrap it on the drum. No garbage cans.
Wrap all the line on the drum
Combust more gff filters
Make stand to hold 2L bottles, can just leave them there

	Papers
	Oxygen –ask Henry to evaluate PAP data- FRAM
Yearly-hourly- compare community structre behavior to ecological variables- Later

	Order current meter after cruise
	

	September cruise
personnel
	Moved to September 28-6 October
Ken
Crissy
Rich-Johnny
Paul-Henry
Erich R and Eric Orenstein

	Proposals
	Weeks from now. MT is meeting next week.

	September cruise Science
	Recover everything
Iris
Water filter standllect larvacean houses in D-samplers to do DNA sequences
Collect aggregates on the seafloor

	Rover/SES comms
	Proof of concept the two communicating with each other
Range to rover wakes it up. Device enable line is not working correctly

	Personnel schedules
	Rich- August 30-Sept 16th 
[bookmark: _GoBack]Crissy- 3-11 September
Colleen- 3-11 September, some time in October
Paul- Aug 28-Sept 5th


 
