Electrical tasks for next FOCE deployment (~mid 2009)

DC-DC Converter Board  - 6 days

Populate 




{2 days}

Initial testing




{3 days}

Integration with Distribution Boards

{1 days}
Junction Boxes (A & B) – 5 days

Both need rewired



{5 days}
Computer Stack – 38 days

Parts arrive


Build/configure stack



{2 days} 


[Software: Linux load – bringup]

{10 days?}
Integration with DC-DC Converter Board
{3 days}

Communication testing to each instrument
{15 days}

Load switching testing to each instrument
{5 days}

Verify temperature and humidity readings
{3 days}
Motor Controllers – 19 days

Bench test initial unit



{2 days}


[Software: control of motors]


{15 days ?}


Integration of magnetic switches

{2 days}

Camera/Strobe/LED – 24 days

Test strobe through Insite GUI

{3 days}

Verify operation of new quad video server
{3 days}

Implement a new camera GUI (Dale’s?)
{15 days}

Interface new IT1000 camera


{3 days}
Electronics Housing – 15 days

Get all parts info to Farley




Assemble [Tom Marion]


{5 days}


Bench test bare system


{5 days}


Integrate instruments [with J-Boxes]

{5 days}

Frame Integration -23 days

Dry test




{3 days}

Wet test




{5 days}


Operational wet tests



{10 days}
