FOCE Mtg April, 28, 2008:
Attendees: Jim Scholfield, Farley Shane, Peter Walz, Xin Zhang, Bill Kirkwood

Farley: 


The pressure housing end is being programmed today for the CNC system. 


The JBox end caps will be done today, the internal structure is already with Chad. 


Internal frame for pressure housing not done, working on it presently.

Group discussion on the fold down time delay section. Peter W felt it was doable and will work with the pilot’s on mechanisms for lowering and raising they will find acceptable. 
Jim S: 


Build of the center section going fine. 

Jim has ½ built a wing section with 3 baffles, this could be our fold-out portion for the Ventana dives. 

Jim will add all the fans! He hadn’t planned on including all of the hardware… we discussed it made it clear we want all of the hardware on the center section possible. 

Wing drawings are still not in the shop. 

Farley (2): 

The Nortek (action item from last week to check on) was not purchased. Peter W said at this point he would prefer to try it than buy another one. If we get stuck we can borrow Jim Barry’s again while a new one is ordered. The June tests will hopefully settle getting a second unit or two of something else. 

Peter W: 

We need to get the toolsled done by mid-May. The current discussions sound like we’ve asked for the end of May. Farley will talk to Larry and be sure he knows we need it for build mid-May. 

Time to select oil for the JBoxes, unless someone says otherwise we’ll go with the standard oil Ventana uses. PW will talk to pilot’s to see if we need to buy oil or if they have enough. 

Vicor for MARS simulation doesn’t fit in the Ventana housing as first thought. He pilot’s are looking for a housing to build a MARS power/comms simulation node. Bill said that Tiburon has two housing used for the Pan and Tilts that might be suitable, we could ask Dale if they are available. 

Chad has the HD camera and lights. It was agreed they should be installed on the center section for the June dives. 

Bill K: 

We spent $150,000 of our budget or about 2/5ths. We still have to build the second FOCE system and the CO2 systems for both. The materials are in house for most of the sections and most of the instruments are already in hand. The Nortek will be a $10K plus purchase and Bill pointed out we need two real electronics housings for the long term (guesstimating $40K for those currently, material and machining). 

Zhang : 


We discussed some of the feedback for his thesis and some changes to be made. 

Meeting ended - peace and harmony prevailing. (  

