
FOCE Team Mtg -- 3/7

Present: WJK, RH, KH, KS, PMW, JS, CK & ETP.

PGB at Hopkins ML this AM to take photos and to meet with Steve Palumbi

Bill K presented plans for meeting with Brantner

Chad thinks we have a deployment comoing up soon!
Jim S:

  - Saw-horses coming Friday.

  - Almost done with most of the parts.

  - Ordering most expanded grates for CHEDs.  1 or 2 left on sea-floor @ MARS.

  - Plans for internal frames at shop.

MARS deployment is April 4th & 5th:

  - Mob on 4/1.
  - FOCE out of the test tank on 3/31.

  - FOCE in the test tank on 3/17.

  - FOCE Final electronics check tank-side on 3/16.

  - FOCE ready for assembly 3/10.

  - Need all parts completed this week.

  - Note: PMW & ETP at sea on 3/14-16.

Question/discussion of how to weigh-down the CO2-ESW line between the reservoir and FOCE.
Software:

  - Kent has been working on control loop software.

      - Gave a nice demo.

      - Had a list of things yet to do.
  - Still on the fence regarding Data Turbine.


