## summary
2012-08-06 | We discussed several potential solutions to ship-LRAUV collision avoidance for the September CANON experiment -- these are arranged relative to requirements on the sheet (requirements & solutions).
The tentative plan is to go with a simple operational approach: the LRAUVs will surface at deterministic times -- i.e., every hour, on the hour, plus or minus 5 minutes -- and the ship will move through the no-fly zone right after GPS fixes, when the LRAUV positions are best known.
This approach is potentially brittle -- ship operations will be restricted if one of the vehicles fails to surface.
Questions to answer:
How often will the Flyer be moving through the no-fly zone?
How long will the Flyer need to be in the no-fly zone?
How much will restricting Flyer's movements impact the science mission?
How much internal clock drift can we expect on the LRAUVs?
All of the other potential solutions require additional transducers to be mounted on both LRAUVs.
This requires engineering time, and other sensors are currently higher priority.
The transducer might be mounted in a long nose on Tethys, but would have to be mounted outside the skin on Daphne (due to the turbulence package).
Outside mounted transducers will increase drag:
reducing overall endurance, and
possibly changing maneuvering so that controller gains need re-tuning.
However, many future deployments will benefit from having acoustic modem or DAT transducers as optional payload.
Using DAT or USBL on the ESP drifter or the ship will reduce uncertainty in LRAUV position throughout deployment.
If we do mount transducers on the LRAUVs, it would probably be worthwhile to mount a DAT on the ESP or the Flyer.

## requirements & solutions
| deterministic surfacing time | comms relay LRAUV DR estimate | DAT on ESP drifter | USBL on ESP drifter | DAT on ship | USBL on ship
Keep vehicle safe | 1 | 1 | 1 | 1 | 1 | 1
position relative to ESP drifter | 0 | 0.5 | 1 | 1 | 0.75 | 0.75
low technical risk | 1 | 1 | 1 | 1 | 1 | 1
does not compromise science mission | 1? | 1? | 1? | 1? | 1? | 1?
does not compromise necessary endurance | 1? | 1? | 1? | 1? | 1? | 1?
avoids time sink (do no distract from getting RSSI or other sensors working) | 1 | 0.5 | 0.5 | 0 | 0.5 | 0
avoid `one time' modifications to vehicle | ? | ? | ? | ? | ? | ?
requires transducer on LRAUVs | 0 | 1 | 1 | 1 | 1 | 1
requires modification to ESP drifter | 0 | 1 | 1 | 1 | 0 | 0
requires modification to Western Flyer | 0 | 0 | 0 | 0 | 1 | 1