## Shore Side
swFOCE task list |  | Project: | 901219
|  | Deadline: | 2013-06-30
Done | Shore Side Power | Due By | Notes | % Comp
No | Building Power - 220 VAC | 2013-05-30 | Lead - Chad |  | 0
No | Building Power - 110 VAC | 2013-05-13 | Lead - Chad |  | 0
No | Install safety switch | 2013-05-30 | Lead - Chad |  | 0
No | Install Diver Lockout (Emer disconnect) | 2013-05-30 | Lead - Chad |  | 0
No | Mechanical Layout | 2013-03-15 | Lead - Farley Bldg Delivered | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Building setup at Hopkins | 2013-05-30 | Lead - Farley w/ Jim S | IIIII | 20
No | Power Management software | 2013-06-01 | Lead - Kent | I | 5
0
Done | Shore Side Elect. Rack | Due By | Notes | % Comp
No | Rack - Move too Hopkins Bldg | 2013-05-15 | Lead - Chad |  | 0
No | Rack - Install KFA power Supply | 2013-04-30 | Lead - Chad |  | 0
No | Rack - Install KFA GF circuit | 2013-04-30 | Lead - Chad |  | 0
No | Rack - Load Test System | 2013-04-30 | Lead - Chad |  | 0
No | Rack - Final Termination of Tether | 2013-06-05 | Lead - Chad |  | 0
No | Rack - Wiring outputs connections | 2013-06-05 | Lead - Chad |  | 0
0
0
0
Done | Shore Side Network | Due By | Notes | % Comp
No | Network - Route internet to pumphouse | 2013-05-30 | Lead - Chad |  | 0
No | Network - Route internet to Bldg rack | 2013-05-30 | Lead - Chad |  | 0
No | Network - Create Stanford acct(s) | 2013-04-30 | Lead - Jamie | IIIII | 20
No | Network - Firewall/Security | 2013-05-15 | Lead - Jamie |  | 0
0
0
Done | Shore Side Computer | Due By | Notes | % Comp
No | Computer - Build | 2013-04-30 | Lead - Karen S | II | 10
No | Computer - Test | 2013-04-30 | Lead - Karen S | II | 10
No | Computer - setup data storage | 2013-04-30 | Lead - Karen S / Tom O / Kent | II | 10
No | Computer - setup data transfer/backup | 2013-04-30 | Lead - Karen S / Tom O / Kent | II | 10
No | Computer - offsite back-up | 2013-05-30 | Lead - Karen S / Tom O / Kent |  | 0
0
0
Done | Shore Side CO2 Enrich Sys | Due By | Notes | % Comp
No | CO2 - Sensor Select/Order | 2013-04-05 | Lead - Chad | IIIIIIIIIIII | 50
No | CO2 - Sensor Testing | 2013-04-10 | Lead - Chad | IIIIIIIIIIII | 50
No | CO2 - Data collect sys | 2013-05-05 | Lead - Chad | II | 10
No | CO2 - data wiring | 2013-04-25 | Lead - Chad |  | 0
No | CO2 Tanks | 2013-05-15 | Lead - Peter W |  | 0
No | CO2 Regulators | 2013-04-15 | Lead - Peter W |  | 0
No | CO2 Tank Rack | 2013-04-15 | Lead - Farley |  | 0
No | CO2 Plumbing / Connectors | 2013-04-15 | Lead - Jim S |  | 0
No | Water line plumbing / spray sys. | 2013-04-15 | Lead - Jim S | IIIIIIIIIIIIIIIIIIIIII | 90
No | Instrument Code | 2013-05-01 | Lead - Kent |  | 0
No | Mixing tank - Level control - automated | 2013-04-25 | Lead - Jim S | IIIIIIIIIIIIIIIIIIIIII | 90
yes | Mixing Tank- Test of seals | 2013-04-05 | Lead - Jim S | IIIIIIIIIIIIIIIIIIIIIIIII | 100
yes | Mixing tank - New n Spare O-Rings | 2013-04-05 | Lead - Jim S | IIIIIIIIIIIIIIIIIIIIIIIII | 100
yes | Mixing Tank- Test of seals | 2013-04-05 | Lead - Jim S | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Mod flanges for connectors | 2013-04-15 | Lead - Farley | IIIIIII | 30
No | Mixing Tank- Move to Hopkins | 2013-04-30 | Lead - Jim S | II | 10
No | Mix Tank - internal brackets | 2013-04-15 | Lead - Farley | IIIIIIIIIIIIIIIIIIIIIII | 95
yes | Purchase flow sensor | 2013-04-01 | Lead - Jim S | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Water line supply | 2013-05-10 | Lead - Farley | I | 5
Done | Software | Due By | Notes | % Comp
No | Task Management | 2013-04-04 | Lead - Kent | IIIIIIIIIIIIIII | 60
No | Concurrency | 2013-04-15 | Lead - Kent (TBD) | IIIIIII | 30
No | Logging | 2013-04-04 | Lead - Kent (Current Focus) | IIIIIIIIIIII | 50
No | Basic Messaging | 2013-04-10 | Lead - Kent (TBD) | II | 10
No | Basic Mess: ZMQ data pub/submess API | 4//12/13 | Lead - Kent (required for GUI enable) |  | 0
No | Basic Mess: config / control API | 2013-06-30 | Lead - Kent (defrd) |  | 0
No | Sensor node Firmware | 2013-04-19 | Lead - Bob H (TBD) |  | 0
No | Sensor node Port Drivers | 2013-06-30 | Lead - Kent (concerns with Bandwidth for streaming) | IIIIIIIIII | 40
No | Virtual serial ports | 2013-04-19 | Lead - Kent (Systemd socat service?) |  | 0
No | GPIO Drivers | 2013-04-26 | Lead - Kent | IIIII | 20
No | Power switching | 2013-04-26 | Lead - Kent |  | 0
No | Memory Management | 2013-06-30 | Lead - Kent | IIIIIII | 30
No | Memory: dynamic allocation | 2013-06-30 | Lead - Kent | II | 10
No | Memory: reference counting | 2013-06-30 | Lead - Kent |  | 0
No | Basic Config: platform ID | 2013-05-15 | Lead - Kent (fall back: compile-config) | II | 10
No | Basic Config: Instru ID | 2013-05-15 | Lead - Kent | II | 10
No | Basic Configu: scheduling | 2013-05-15 | Lead - Kent | II | 10
No | Basic Config: Experimetn config | 2013-05-15 | Lead - Kent | II | 10
No | power management | 2013-06-30 | Lead - Kent (low Priority) |  | 0
No | Control System | 2013-06-30 | Lead - Kent (TBD) |  | 0
No | Drivers: core inst. (ph,CTD,Par,flow,ADCP) | 2013-05-15 | Lead - Kent | I | 5
No | Drivers: Actuators (ESW pump, flomotor, valves) | 2013-05-15 | Lead - Kent | I | 5
No | Drviers: sys monitors (volt, relay, GF, current) | 2013-05-15 | Lead - Kent depends hdwe | I | 5
No | Drivers: Environ (RH, H2O, Temp) | 2013-06-15 | Lead - Kent depends hdwe | I | 5
No | Metadata | 2013-06-30 | Lead - Kent (TBD) defer |  | 0
No | Image handling | 2013-06-30 | Lead - Kent (TBD) |  | 0
No | Shoreside: Sys Status | 2013-06-30 | Lead - Kent |  | 0
No | Shoreside: Archive sync | 2013-06-30 | Lead - Kent |  | 0
No | Shoreside: SSDS ingest | 2013-06-30 | Lead - Kent defer |  | 0
No | Shoreside: log access | 2013-06-30 | Lead - Kent |  | 0
No | Shoreside: platform config | 2013-06-30 | Lead - Kent defer |  | 0
No | Shoreside: GUI | 2013-06-30 | Lead - Karen |  | 0
No | Web page: xFOCE | 2013-06-30 | Lead - Karen / Ed / Bill | IIIIIIIIIIIIIIIIII | 75
No | Web page: swFOCE | 2013-06-30 | Lead - Karen / Ed | IIIIIIIIIIII | 50
0

## Cable-Hose
swFOCE task list |  | Project: | 901219
|  | Deadline: | 2013-06-30
Done? | Cable and Hose | Due By | Notes | % Comp
No | Install pH Hose | 2013-05-15 | Lead - Farley w/ Peter W |  | 0
No | Install O2 Hose | 2013-05-15 | Lead - Farley w/ Peter W |  | 0
No | RE-route cable | 2013-05-30 | Lead - Farley w/ Peter W |  | 0
No | Terminate Ends | 2013-06-10 | Lead - Farley w/ Chad |  | 0
0
0
pH Sensor Analysis
Done? | Wet Connector | Due By | Notes | % Comp
Yes | Seabird 18S lab qualification | 2013-03-25 | Lead - Thom | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Seabird 18s versus HRpH test @ Hopkins | 2013-04-10 | Lead - Thom |  | 0
Yes | 18S doc pinout/ serial protocol | 2013-03-22 | Lead - Thom | IIIIIIIIIIIIIIIIIIIIIIIII | 100
Yes | KFA aux port pinout | 2013-03-22 | Lead - Chad | IIIIIIIIIIIIIIIIIIIIIIIII | 100
Yes | refit HRpH | 2013-03-22 | Lead - Thom | IIIIIIIIIIIIIIIIIIIIIIIII | 100
Yes | refit HRpH: new glass electrodes | 2013-03-22 | Lead - Thom | IIIIIIIIIIIIIIIIIIIIIIIII | 100
Yes | refit HRpH: stainless drilled | 2013-03-22 | Lead - Parker | IIIIIIIIIIIIIIIIIIIIIIIII | 100
Yes | refit HRpH: rebuild 2 HRpH units | 2013-03-22 | Lead - Thom | IIIIIIIIIIIIIIIIIIIIIIIII | 100
Yes | KFA - connector / cables | 2013-03-25 | Lead - Peter W | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Bio-foul sleeve removal - Durafets | 2013-06-30 | Lead - Thom - Plan change from Barry Lab |  | 0
No | Simple software for data log and read | 2013-06-30 | Lead - Thom |  | 0
No | Setup Hopkins digi serial service | 2013-06-30 | Lead - Thom |  | 0
No | Test tank - stab/drift 18S versus HRpH | 2013-04-05 | Lead - Thom | IIIIII | 25
No | pH sensor calibration | 2013-04-05 | Lead - Thom |  | 0
No | acid/base e-field test | 2013-04-08 | Lead - Thom |  | 0
No | deployment - Hopkins | 2013-04-08 | Lead - Thom / Matsumoto (in situ test at deployment) |  | 0
No | recovery - Hopkins | 2013-04-12 | Lead - Thom / Matsumoto (in situ test at recovery) |  | 0
No | Data analysis: event log | 2013-04-15 | Lead - Ed / Thom |  | 0
No | Data analysis: retrieval | 2013-04-15 | Lead - Thom |  | 0
No | Data analysis: pH | 2013-04-15 | Lead - Ed / Thom |  | 0
No | Post recovery calibration | 2013-04-15 | Lead - Ed / Thom |  | 0
0
0
0
MBARI Connector
Done? | Wet Connector | Due By | Notes | % Comp
No | configure the Rx board for 18S | 2013-04-15 | Lead - Thom |  | 0
No | re-layout boards form factor | 2013-04-30 | Lead - Thom |  | 0
No | test setup | 2013-04-30 | Lead - Thom |  | 0
No | finish board bring up software | 2013-05-05 | Lead - Thom |  | 0
No | data comms, isr software | 2013-05-05 | Lead - Thom |  | 0
No | config power manage transmit controller | 2013-05-10 | Lead - Thom |  | 0
No | diagnostics software | 2013-05-15 | Lead - Thom |  | 0
No | unit testing | 2013-05-20 | Lead - Thom |  | 0
No | unit packaging design | 2013-04-15 | Lead - Thom/Bill |  | 0
No | cables/ connectors | 2013-04-10 | Lead - Thom |  | 0
No | pressure test | 2013-05-10 | Lead - Thom |  | 0
No | test tank dunk testing | 2013-05-15 | Lead - Thom |  | 0
No | shoreside test jig for instrument validation | 2013-06-15 | Lead - Thom |  | 0
No | calib and meta data storage scheme | 2013-05-30 | Lead - Thom |  | 0
No | util puck protocol meta data stor/retrieve | 2013-05-30 | Lead - Thom |  | 0
No | unit potting tool design | 2013-04-20 | Lead - Bill |  | 0
No | tool build | 2013-04-30 | Lead - Bill |  | 0
No | assemble deployable units | 2013-05-30 | Lead - Bill |  | 0
0

## Subsea Nodes
swFOCE task list |  | Project: | 901219
|  | Deadline: | 2013-06-30
Done? | Central node | Due By | Notes | % Comp
Yes | Finish Electrical design | 2013-03-25 | Lead - Chad | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Layout Board | 2013-03-29 | Lead - Chad w/ jose | IIIIIIIIIIIIIIIIIIIIII | 90
No | Fab Board | 2013-04-10 | Lead - Chad |  | 0
No | Populate board | 2013-04-12 | Lead - Chad |  | 0
No | Test Board | 2013-04-15 | Lead - Chad |  | 0
No | Write Code | 2013-04-20 | Lead - Bob / Kent - messaging |  | 0
No | Integration | 2013-04-20 | Lead - Chad/Bob/Kent |  | 0
No | Housing & endcap design | 2013-04-05 | Lead - Farley |  | 0
No | Housing& endcap fab | 2013-04-20 | Lead - Farley |  | 0
No | Cable order | 2013-04-10 | Lead - Chad On order - Due early June | II | 10
No | Internal housing frame design | 2013-04-05 | Lead - Farley |  | 0
No | Internal frame build | 2013-04-20 | Lead - Farley |  | 0
No | System wiring and build | 2013-04-25 | Lead - Chad Wiring diagrams complete |  | 0
0
0
0
Done? | Gateway node | Due By | Notes | % Comp
Yes | Fab - Proto | 2013-03-29 | Lead - Chad | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Populate | 2013-04-05 | Lead - Chad w/ jose | IIIIIIIIIIIIIIIIIIIIII | 90
No | Initial test | 2013-04-10 | Lead - Chad | IIIIIIIIIIII | 50
No | Write Code | 2013-04-15 | Lead - Kent |  | 0
No | test | 2013-04-18 | Lead - Kent |  | 0
No | Electrical Deisgn Final | 2013-04-25 | Lead - Chad |  | 0
No | Layout final | 2013-04-27 | Lead - Chad |  | 0
No | Fab final | 2013-05-05 | Lead - Chad |  | 0
No | Populate final | 2013-05-08 | Lead - Chad |  | 0
No | Initial test of final | 2013-05-10 | Lead - Chad |  | 0
No | code change | 2013-05-12 | Lead - Kent |  | 0
No | Test final | 2013-05-15 | Lead - Kent |  | 0
No | Cable selection | 2013-04-25 | Lead - Chad Due early June / on order | II | 10
No | Housing Design | 2013-04-20 | Lead - Farley | IIIII | 20
No | Housing Build | 2013-05-05 | Lead - Farley |  | 0
No | Integration | 2013-05-10 | Lead - Chad |  | 0
No | Setup Open source fab | 2013-06-30 | Lead - Chad |  | 0
0
Done? | Sensor node | Due By | Notes | % Comp
No | Write Code - Proto | 2013-04-05 | Lead - Bob |  | 0
No | Test | 2013-04-10 | Lead - Bob / Kent |  | 0
No | Electrical Design (final) | 2013-04-15 | Lead - Chad | IIIIIIIIIIIIIIIIII | 75
No | Layout Final | 2013-04-20 | Lead - Jose |  | 0
No | Fab | 2013-04-25 | Lead - Chad |  | 0
No | Populate | 2013-05-05 | Lead - Chad |  | 0
No | Initial test | 2013-05-08 | Lead - Chad |  | 0
No | Code Udate | 2013-05-10 | Lead - Kent |  | 0
No | Update code test | 2013-05-15 | Lead - Bob |  | 0
No | Cable select/order | 2013-04-15 | Lead - Chad On order / due early June | II | 10
No | Housing Design | 2013-04-15 | Lead - Farley | IIIII | 20
No | Housing Build | 2013-04-30 | Lead - Farley |  | 0
No | Integration | 2013-05-05 | Lead - Chad/Kent/Bob |  | 0
No | Setup open source package | 2013-06-30 | Lead - Chad | II | 10
0
0
0
0
Done? | swFOCE Chamber | Due By | Notes | % Comp
No | Frames | 2013-04-30 | Lead - Jim S |  | 0
No | Acrylic Panels | 2013-04-15 | Lead - Jim S |  | 0
No | Par Sensor | 2013-04-15 | Lead - George w/ Chad |  | 0
No | CTDO - internal | 2013-04-15 | Lead - George w/ Peter W and Chad |  | 0
No | Hardware - hinges | 2013-04-15 | Lead - Jim S |  | 0
No | Anchors | 2013-04-15 | Lead - Jim S |  | 0
No | Side skirts / mat | 2013-04-15 | Lead - Jim S |  | 0
No | Sys build wiring | 2013-05-10 | Lead - Chad | IIIII | 20
Yes | Purchase flow sensor | 2013-04-01 | Lead - Jim S | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Mod flow sensor for depth | 2013-04-15 | Lead - Jim S |  | 0
0
Done? | Main Elec Housing | Due By | Notes | % Comp
Yes | Electrical Design | 2013-04-10 | Lead - Chad | IIIIIIIIIIIIIIIIIIIIIIIII | 100
Yes | Internal wiring diagram | 2013-04-10 | Lead - Chad | IIIIIIIIIIIIIIIIIIIIIIIII | 100
No | Housing Design | 2013-04-05 | Lead - Farley | II | 10
No | Housing Build | 2013-04-30 | Lead - Farley | II | 10
No | Cable select/order | 2013-04-15 | Lead - Chad On order / Due early June | II | 10
No | Internal Frame design | 2013-04-15 | Lead - Farley | II | 10
No | Ingernal frame build | 2013-04-30 | Lead - Farley |  | 0
No | Sys build wiring | 2013-05-05 | Lead - Chad |  | 0
0
0
0
Done? | System Elements | Due By | Notes | % Comp
No | Integrate all nodes | 2013-05-15 | Lead - Chad |  | 0
No | instrument cabling | 2013-05-05 | Lead - Chad w/ Peter W |  | 0
No | Camera and Light testing | 2013-04-10 | Lead - Chad |  | 0
No | Camera housing | 2013-04-25 | Lead - Farley | II | 10
No | Lighting mounts | 2013-04-25 | Lead - Farley |  | 0
0
0
0
Done? | ESW Valve box | Due By | Notes | % Comp
No | Select and buy valves | 2013-04-15 | Lead - Farley |  | 0
No | Design Housing | 2013-04-20 | Lead - Farley |  | 0
No | Fab Housing | 2013-05-15 | Lead - Farley |  | 0
0
No | Connectors | 2013-04-30 | Lead - Farley w/ Chad On order / Due early June |  | 0
No | Cabling | 2013-04-30 | Lead - Chad On order/ Due early June |  | 0
No | Hoses n conncetors | 2013-04-30 | Lead - Farley w/ Peter W |  | 0
No | Testing | 2013-05-20 | Lead - Farley w/ Peter W |  | 0
0
0