## labor
ME
Task
|  | 1.1 | MB systems
|  | 1.2 | embed metadata
|  | 1.3 | VARS for stills
|  | 1.4 | Google Earth
|  | 1.5 | AVED
|  | 1.6 | box mosaic for MPA
|  | 1.7 | Add sensors
|  | 2.1 | TRN
|  | 2.2 | tune and tweak
|  | 2.3 | bowthruster
|  | 2.4 | Horner
|  | 3.1 | reconfig for midwater
|  | 3.2 | zoom/focus, strobe switch
|  | 3.3 | field test with EK-60
|  | ME | SE | EE | task sum | task sum | task sum | ME Tech | SE Tech | EE Tech | Ship time | Brett | Jon | Mike McCann | Rob | Brian | Danelle | Alana | Dave C. | Jim S. | ET
Refine
1.1 | MB systems | 1 | 10 | 0 | [7 empty] | 1 |  |  | 10 | [7 empty] | 0
1.2 | embed metadata | 2 | 5 | 0 | [7 empty] | 2 |  |  |  | 5 | [6 empty] | 0
1.3 | VARS for stills | 2 | 30 | 0 | [7 empty] | 2 |  |  |  | 30 | [6 empty] | 0
1.4 | Google Earth | 1 | 10 | 0 | [7 empty] | 1 |  | 10 | [8 empty] | 0
1.5 | AVED | 1 | 26 | 0 | [7 empty] | 1 |  |  |  |  | 26 |  |  |  |  | 54 | 486
1.6 | box mosaic for MPA | 5 | 15 | 0 | [7 empty] | 5 |  |  | 15 | [7 empty] | 0
| subtotal | 0 | 0 | 0 | 12 | 96 | 0 | [15 empty] | 0
|  | 0 | 0 | 0 | 108 | 864 | 0 | [15 empty] | 0
| Terrain Following | 0 | 0 | 0 | [18 empty] | 0
2.1 | TRN | 2 | 5 | 0 | [7 empty] | 2 |  |  | 5 | [6 empty] | 14 | 126
2.2 | tune and tweak | 1 | 15 | 0 | [7 empty] | 1 |  |  | 15 | [6 empty] | 32 | 288
2.3 | bowthruster | 25 | 5 | 10 | [7 empty] | 5 | 20 |  | 5 |  |  | 10 |  | 15 | 5 |  | 0
| subtotal | 0 | 0 | 0 | 28 | 25 | 10
|  | 0 | 0 | 0 | 252 | 225 | 90
| subtotal | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
| Project Management | 5 | 0 | 0 | [7 empty] | 5 | [10 empty] | 0
|  | 0 | 0 | 0 | [18 empty] | 0
|  | 0 | 0 | 0 | [18 empty] | 0
| Days | 44 | 111 | 10 |  |  |  | 0 | 0 | 0 | 0 | 24 | 20 | 10 | 40 | 35 | 26 | 10 | 0 | 15 | 5 | 100 | 900
| Hours (9 hrs/day) | 396 | 999 | 90 |  |  |  | 0 | 0 | 0 | 0 | 216 | 180 | 90 | 360 | 315 | 234 | 90 | 0 | 135 | 45 | 900
[12 empty] | Brett | Jon | Mike McCann | Rob | Brian | Danelle | Alana | Dave C. | Jim S.
AUV operations:
2 days for MPA box
4 days for Midwater

## Supplies
ex
Supplies:
Computer
Mac laptop to run MB Systems and AVED Classification
1.5, 1.1 | Needs 8 GB memory, XP parallels and Matlab | 3753
Sensors
o Biodiversity initiative needs environmental data
task 1.7 | § Seabird Seacat 19plus V2 CTD | 11700
task 1.7 | § Seabird SBE 43 DO sensor | 4900
task 1.7 | § Wetlabs ECO-FLNTU(RT)D Chlorophyll and Turbidity sensor | 4800
· Syntactic foam
task 1.7 | o Replace 3km rated foam in AUV | 3200
| § Foam to offset instruments, Ideal Instrument TG-28A | 2500
task 2.3 | 8" long midbody hull section with clamps and rings | 2100
| 1 HT Servo size 100 thrusters | 4500
| Sevo controller boards | 4800
· AUV supplies
task 3.1 | o Wet cabling to flip midbody end for end | 2800
task 3.2 | Camera lens upgrade: Nikon 17-35 | 1750
| motors, gears, controller | 1200
| travel to Ocean Sciences | 1000
Task | MARS port fees | 12000
61003