Benthic Imaging AUV
Meeting Minutes –13 Nov. 2008

1. General

a. Issues

i. Resources

1. As of 10/15/08: Jon has 241 hours, Kent is 27 hours over, Rob has 180 hours, Jim has 223 hours, and Alana has 51 hours

2. 2008 Ship days: Lobos Nov 21 (Fri), Nov. 24 (Monday),  Dec. 4th (Thurs), Dec 22, 23 (Mon, Tues)

3. 2009 Ship days: March 2, March 30, April 13, June 10, Oct 5, Oct 22

4. Alana gone 21-28

5. Kent gone 24- Dec 2

6. Supply budget is in the RED
ii. Design Issues

1. X-port initialization issues

a. Change to active low

2. USBL ready
3. Need tow point
4. Need forward bulkhead parts
5. Strobe reflector

6. Wifi

a. Esteem 900 MHz
7. environment in ball, e.g. humidity, pressure/vacuum

iii. Misc.

2. Tasks 

a. Add lasers and modem early next year

b. WBS

3. Data 
4. Schedule

a. Ship days: Nov. 24 (Monday),  Dec. 4th (Thurs), Dec 22, 23 (Mon, Tues)
b. Milestones: 

i. Demonstrate camera system meets requirements in tank

ii. Lock down initial camera/strobe configuration

iii. CDR

iv. Get Camera/strobe under MVC control

v. Demo AUV in Tank

vi. Plan ’09 work – submit proposal
vii. ROV camera test
viii. First sea test

ix. First photo mosaic

x. First science dataset

