08/27/2015

Topics:

- Unit builds

  - Denis begins re-build of unit (2 or 3?)

  - Update inventory sheet

  - Update CCE acoustic asset sheet

- Mobo

  - Expected in house 3rd week of Sept – schedule risk

- Build Up

  - Spheres ready early-August.

  - Pressure sensors expected 3rd week of Sept – schedule risk

  - Dead weight test pressure sensors?

- Software

  - Variable bounding - COMPLETE

  - Comms protocol - WIP

- Batteries

  - Have 7 (3 old, 4 new). 4 on order. New batts need new brackets (available Aug).

  - Additional packs covered under cont margins

- Argos: Test all remaining trackers - COMPLETE

Misc:

- Config sheet for CCE acoustics - COMPLETE

Cruises:

Paragon ride Late August to locate BED 1 via modem- Alana

Oct 5,6,20 Carson (may deploy 400m BED on 10/6)