901006 Benthic Event Detectors
Rating: 1
MT contact: Doug/Andy
Management Team Feedback
General Comments:
The management team supports the build out and testing of BEDs in 2014. The Wave
Glider work is also supported.
Charlie Paull has been asked to adjust his portfolio of projects so they are spread over
multiple years. One possible scenario is that the Coordinated Canyon Experiment will be
postponed until 2015. If this happens, can milestones 4 and 5 be deferred to 2015?

2014 Proposal Process – Phase I MT Feedback

For Phase 2 please address the following:
We would like to see a review of the processed suite of instrument data to ensure that the
quality and integrity meet science requirements. See Andy Hamilton to arrange this.
A review of the data will be occurring as part of the scheduled critical design review in 2013.

Alana Sherman’s time (300 hours) was requested in the proposal but not entered in the
budget. Please add the necessary hours to the budget.
This has been adjusted in the budget entry website. 

Adjust the labor and project budget requests as needed to accommodate Charlie’s overall
revised suite of project plans (e.g., if milestones 4 and 5 are deferred
[bookmark: _GoBack]This has been updated. Please reference the table below. Additionally, budget entry for labor and expenses has been updated. Funds to build an additional 2 BEDS have been added to the budget based on feedback and discussions with the Management Team and Charlie Paull.  The intent is to provide additional instruments to use during the Wave Glider tests which will now presumably continue into early 2015, and yet still have enough BED instruments for the Coordinated Canyon Experiment deployments (~October 2015). It will be less work in the long run to fabricate all the instruments at once.
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	Software and hardware upgrades completed
	
Monument and Bed experiment
	7 additional BEDs constructed
	Support BED deployment in canyon throughout year 
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