## Sheet1
Assembly # | Assembly name | BEDS#2 | BEDS#3 | BEDS#1
| Built # | 1 | 3 | 4
| Built Date | 2013-04-10 | 2013-12-06 | 2013-12-09
10020895-AS1 | BEDS-Cylinder Assembly |  | AS1 SN003 12/2013 | AS1 SN004 12/2013
10020895-AS2 | Electropack Assembly | AS2 SN001 03/08/2013 | AS2 SN003 11/26/2013 | AS2 SN004 12/9/2013
| Batteries Model | BCX85DD | CSC93DD | CSC93DD
| Batteries Part# | 3B0076-XB | 3B0036-XB | 3B0036-XB
| Batteries batch | 2231701 | 2334026 | 2334026
Batteries Received
| Voltage AS3L/AS3R | 27.50 V/ 27.499V | 27.18V / 27.19V | 27.16V / 27.16V
10020895-AS3L | Battery End Cap Assembly |  | AS3L SN003 11/26/2013 | AS3L SN002 4/8/2013
10020895-AS3R | Battery End Cap Assembly |  | AS3R SN003 11/26/2013 | AS3R SN002 4/8/2013
10020895-AS4 | Mother Board Plate Assembly |  | AS4 SN003 12/05/2013 | AS4 SN002 4/8/2013
| Mother Board Part# |  | 10020895-MOB1 Rev1 | 10020895-MOB1 Rev1
| Mother Board SN | SN002 4/1/2013 | SN003 12/4/2013 | SN001 02/1/2013
| Inductor | L1=100uH | L1=22uH | L1=47 uH
| MP6050 Board | 3.3 Mod#4 |  | 3.3 Mod#3
| Persistor model | PERCF21M | PERCF21M | PERCF21M
| Persistor SN | CF2-12325 | CF2-12327 | CF2-12321
| CF Card SN | SN002 | SN003 12/05/2013 | #1
| Coin Cell |  | CR2032 June 2012
10020895-AS5 | Modem Plate Assembly | AS5 SN001 3/10/2013 | AS5 SN003 11/26/2013 | AS5 SN002 4/8/2013
| Modem Part # | ATM-903-LS1 | ATM-903-LS1 | ATM-903-LS1
| Modem SN | 59016 | 59017 | 59019
10020895-AS6 | Homer Battery Plate Assembly | AS6 SN001 3/6/2013 | AS6 SN003 11/26/2013 | AS6 SN002 4/4/2013
| Battery Type | 7835-007 | 7835-007 | 7835-007
| Battery Voltage (Nominal) | 14.5 |  | 14.5V
| Battery SN | 270053-16 | 270053-13 | 270053-19
| Battery Exp. Date | 10/2015 | 10/2015 | 10/2015
| Battery Tested Date | 42/2010 |  | 42/2010
| Battery Tester | GD |  | GD
| Battery (other property) |  |  | CPN:640-8515
10020895-AS7 | Homer PCB Plate Assembly | AS7 SN001 04/10/2013 | AS7 SN003 11/26/2013 | AS7 SN002 4/8/2013
| Homer ID | ID37 | ID27 | ID44
| Homer PCB SN | 273572-080 | 273572-129 | 251082-424
| Homer PCB Tested | 9/7/12 | 7-7-12 | 2-3-8
10020895-AS8 | End Cap Homer Assembly | AS8 SN002 4/10/2013 | AS8 SN003 12/06/2013 | AS8 SN1H 03/08/2013
| Transducer type | 7815-055-A6 | 7815-055-A6 | 7815-055-A4
| Transducer SN | 279767-038 | 279767-048 | 253161-057
| Pressure Sensor Part# | US331-000004-070BA | US331-000004-070BA | US331-000004-070BA
| Pressure Sensor SN | 8-010813F004 | 8-010813F009 | 8-010813F012
| Diaphragm | 10020865-017 Rev1 | 10020865-017 Rev2
| Diaphragm Cover | 10020895-016 Rev2 | 10020895-016 Rev3
10020895-AS9 | End Cap Modem Assembly | AS9 SN2M 04/10/2013 | AS9 SN003 12/06/2013 | AS9 SN1M 03/08/2013
| Modem Transducer Model | SDCR AT-12RT | SDCR AT-12RT | XDCR AT-12RT
| Modem Transducer Part# | C-400-21 | C-400-21 | C-400-21
| Modem Transducer SN# | 61887 | 59092 | 59089
Source assemblies
| Transponder | TZ/OBC | TZ/OBC | TZ/OBC
| Type | 7815-000-06 | 7815-000-06 | 7815-000-06
| Manufacturer | Sonardyne | Sonardyne | Sonardyne
| Homer ID | ID37 | ID27 | ID44
| Homer SN | 279729-145 | 279729-148 | 253160-034
| Inner Housing | 279729-145 | 279729-148
03/26/2014 Ducer SN 61887 from repair installed in BEDS#2

## Slot Allocation
Battery Slot Allocation and Recording
Assembly: | AS2 SN003
Slot# | Model | Part# | Batch# | SN# | Voltage 11/26/2013 | Voltage 5/9/2014 | Note
Slot L1 | CSC93DD | 3B0036-XB | 2334026 | 3027 | 3.886 | 3.859 | positive wire missing; signs of corrosion under paper disk
Slot L2 | same | same | same | 7331 | 3.886 | 3.86 | failed cell; 2 pitted areas on the edge on positive side; electrolyte leaked out
Slot L3 | same | same | same | 7305 | 3.886 | 3.344
Slot L4 | same | same | same | 7306 | 3.885 | 3.85 | severe connector corrosion
Slot L5 | same | same | same | 7339 | 3.885 | 3.061
Slot L6 | same | same | same | 7340 | 3.885 | 3.739
Slot L7 | same | same | same | 7334 | 3.885 | 3.852
Slot R7 | same | same | same | 3026 | 3.885 | 3.856
Slot R6 | same | same | same | 7332 | 3.885 | 3.856 | other side of failed cell in slot L2
Slot R5 | same | same | same | 7325 | 3.885 | 3.856
Slot R4 | same | same | same | 7336 | 3.885 | 3.856
Slot R3 | same | same | same | 7335 | 3.886 | 3.856
Slot R2 | same | same | same | 3029 | 3.886 | 3.857
Slot R1 | same | same | same | 7327 | 3.886 | 3.856