## Sheet1
Cat | Description | NN per BEDS | part number | Inventory | SN | note | need | ordering | due date
Electronics
| Mother board |  | 10020895-MOB1 | 1 | SN002 | in Bob office
|  |  |  | 1 | SN003 | flooded, spare
|  |  |  | 1 | SN004 | new, untested
|  | 1 | 10020895-MOB2 |  |  |  | 3 | 4 | 2015-09-18
[7 empty] | 6 | 6 | 2015-11-01
| Battery pack Board | 2 | 10020895-BPC1 | 2 |  | in Bob office
|  |  |  | 5 |  | assembly box
[8 empty] | 20 | 2015-09-11
| Modem | 1 |  | 1 |  | from battery leak unit
|  |  |  | 1 |  | in Bob office
|  |  |  | 3 |  | from Brian
|  |  |  | 4 |  | in Brian office
| Compact flash memory | 1 |  | 1 |  | assembly box
|  |  |  | 1 |  | in Bob office
|  |  |  | 7 |  | from Brian
3
| Persistor boards | 1 |  | 1 |  | assembly box
|  |  |  | 1 |  | from battery leak unit
|  |  |  | 9 |  | from Brian
| InvenSense board | 1 | MPU6050 | 1 |  | Indtek, soldering guide
|  |  |  | 1 | SN006 | assembly box
|  |  |  | 1 | SN007 | assembly box
|  |  |  | 3 |  | from Brian
5
| Homer | 1 |  | 1 |  | from battery leak unit
|  |  |  | 1 |  | in Bob office
|  |  |  | 5 |  | from Larry
3
| Homer lithium battery upgrade | 1 |  | 5 |  | from Dale
5
Mechanical parts, fabricated
| Battery-End-Cap |  | 10020895-010Rev0 | 2 |  | in Bob office
|  |  |  | 2 |  | in the shop
|  | 2 | 10020895-010Rev1 | 10 |  | shelf (5 mod, 5 new)
8
| Base-Plate | 2 | 10020895-011Rev0 | 6 |  | assembly box
|  |  |  | 2 |  | Bob office
|  |  |  | 2 |  | from battery leak unit
12
| Side-Base-Plate | 2 | 10020895-012Rev0 | 6 |  | assembly box
|  |  |  | 2 |  | Bob office
|  |  |  | 2 |  | from battery leak unit
12
| MPU-6050-Bracket | 1 | 10020895-013Rev0 | 12 |  | assembly box
|  |  |  | 1 |  | Bob office
|  |  |  | 1 |  | from battery leak unit
| Modem-Bracket |  | 10020895-014Rev0 | 2 |  | assembly box
|  |  |  | 2 |  | Bob office
|  |  |  | 2 |  | from battery leak unit
|  | 2 | 10020895-014Rev1 | 10 |  | assembly box
6
| Persisitor-Bracket | 1 | 10020895-015Rev0 | 10 |  | assembly box
| (also CF card retainer) |  |  | 1 |  | Bob office
|  |  |  | 1 |  | from battery leak unit
Harnesses
| MB power, left (3") | 1 |  | 1 |  | Bob office |  | 10 | due 9/16/2015
| MB power, right (7") | 1 |  | 1 |  | Bob office |  | 10 | due 9/16/2015
| Homer power extension | 1 |  | 1 |  | Bob office |  | 10 | due 9/16/2015
| BEDS Modem power cable | 1 |  | 1 |  | Bob office
|  |  |  | 1 |  | from battery leak unit
3
| BEDS Modem serial cable | 1 |  | 1 |  | Bob office
|  |  |  | 1 |  | from battery leak unit
3
| BEDS Transponder termination | 1 |  | 1 |  | Bob office
4
| Pressure sensor termination | 1 |  |  |  |  | 5
Legend:
October 2015 deploylemt: 5x units
2016: 5 units + 1 spare parts set