## Sheet1
Description | Part # | Qty in house | Qty Needed | Quote Recv'd? | PO? | Unit Cost | Total Cost | Vendor | POC | Notes
Spheres - modified per MBARI drawing 1006789 | HBF18-1500 | 0 | 8 | Y | N | 1793 | 14344 | DeepWater Buoynacy | Bird | Lead time 6 wks
Sphere End Caps |  | 0 | 16 | N |  |  |  |  | Bird |  | highlighted is budgeted for 2015
Housing |  | 7 | 0 |  |  |  | 0 |  | Bird
End caps |  | 0 | 14 | N |  |  | 0 |  | Bird
Apater Ring |  | 0 | 14 | N |  |  | 0 |  | Bird
Galvanic Time Releases |  | 0 | 11 | Y |  | 100 | 1100
0
Benthos Modem and remote xducer w/ stainless stem | ATM-903-LS1 | 1 | 6 | Y | Y | 6375 | 38250 | Benthos | Kieft | actual $41,073.0 w/ tax and shipping
Homer Beacon 7815 | 620-6431 | 3 | 5 | N | N | 1820 | 9100 | Sonardyne | Graves
Lithium Battery pack | 640-8515 | 3 | 5 | N | N | 359 | 1795 |  | Graves
0
IMU - 206xx |  | 0 | 12 | N | N | 15 | 180 | Invensense | Herlien
2006xx carrier board |  | 0 | 12 | N | N | 150 | 1800
IMU - old |  | 15 | 0
Batteries | 3B0076-XB | 4 | 8 | Y | Y | 1400 | 11200 |  | Klimov | Actual $12,343.53 incl. pilot run Delivery 3 sets in Feb, 4 sets in April, 4 sets in September
CPU Board | PERCF21M | 3 | 7 | Y | Y | 395 | 2765 | Persistor | Kieft | Peristor.com
CF Card SanDisk Extreme 32GB 60BM/s | SDCFX-032G-X46 | 3 | 5 | Y | Y | 99 | 495 | Amazon/online | Kieft
Pressure Sensor | US331-000004-070BA | [5 empty] | 0 |  | Klimov
SeaTag TT solar Argos | ST-MOD/ST-MR | 0 | 4 | Y | Y | 2250 | 9000 | Desert Star | Kieft
SeaTag Programmer | TBD | 0 | 1 | Y | Y | 2000 | 2000 | Desert Star | Kieft
Freight/Tax/Other |  |  | 1 |  |  | 537
Grand Total | [6 empty] | 92029