## Sheet1
Rachel Carson
| 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-10-21 | 2015-10-22
Participant | CKP | CKP | CKP | CKP | CKP
Participant | bar: 2015-10-05 to 2015-10-21
Participant | 2015-10-05: Brian Kieft; 2015-10-06: Brian Kieft; 2015-10-20: Brian Kieft
Participant | 2015-10-05: Kurt Rosenberg; 2015-10-06: Kurt Rosenberg; 2015-10-07: Kurt Rosenberg
Participant | 2015-10-05: USGS; 2015-10-06: USGS; 2015-10-07: USGS
Participant | 2015-10-05: USGS; 2015-10-06: USGS; 2015-10-07: USGS
Participant | 2015-10-05: USGS; 2015-10-06: USGS; 2015-10-07: USGS
Participant | 2015-10-05: USGS; 2015-10-06: USGS; 2015-10-07: USGS
Participant | 2015-10-05: Larry Bird; 2015-10-06: Larry Bird; 2015-10-21: Larry Bird
Participant | 2015-10-07: Jim Barry; 2015-10-22: Jim Barry
Participant | 2015-10-07: Patrick Whaling; 2015-10-22: Patrick Whaling
Participant | 2015-10-07: Kurt Buck; 2015-10-22: Kurt Buck
Participant | 2015-10-07: Chris Lovera; 2015-10-22: Chris Lovera
Participant | 2015-10-20: Jingping Xu
Participant | 2015-10-20: OUC
Participant | 2015-10-20: OUC
Participant | 2015-10-21: AMT-Tech?
Participant | 2015-10-05: NERC?
Participant | 2015-10-05: NERC?
Participant | 2015-10-05: NERC?
tasks | 2015-10-05: STED; 2015-10-06: STED
| BED | BED |  | BED
| NERC 500 | USGS 300 | USGS 800 | OUC 1500
|  |  | 1300 (Barry) recovery |  |  | 1300 (Barry) Deploy
AMT's satellite
Western Flyer
| Oct 13 to Oct 16 |  | Oct 27- Oct 28th
| CKP |  | EVERYBODY on call
RG
Mark Chaffey
Tom O'Reilly
Chris Lovera
Patrick Whaling
Kurt Buck
Jim Barry
Larry Bird
AMT tech
Dan Parsons
Krystle Anderson
Esther
tasks | 2015-10-05: BIN; 2015-10-07: Completion of deployment
1900 m (Jim Barry)
| Main AMT/BED frame |  | check BIN status
| McLane profiler |  | check AMT status
locate/talk to BEDS