## TOTAL RESOURCES 2014-2017 CCE
Total CCE Expenses 2014-2017
CCE Activity Paull's proposal 2014-2017 | 341372.22 | See Paull's proposal CCE 2014-2017 Worksheet
Additional Costs (with IRS Traps) | 133770 | See Additional Costs CCE2014-2017 worksheet
Additional Costs (with McLane traps) | 208570 | See Additional Costs CCE2014-2017 worksheet
Total, wih IRS traps | 475142.22
Total, with McLane traps | 549942.22
External cash sources (NERC) | 400000
2014-2017 CCE net expenses cost, wih IRS traps | 75142.22
2014-2017 CCE net expenses cost with McLane traps | 149942.22
Total CCE LABOR 2014-2017
DAYS
EE | 96
SE | 164
ME tech | 15
Etech | 45
Mtech | 25
Machine Shop | 20
Total CCE SHIPTIME 2014-2017
DAYS
Western Flyer | 26
Rachel Carson 10-hour days | 24
Rachel Carson 24-hour days | 12
Paragon | 27

## Paull's proposal 2014-2017 CCE
CCE ACTIVITY 1 (MBARI-NERC-USGS MONTEREY CANYON EXPERIMENT) 2014-2017
| 2014 | [5 empty] | 2015 | [6 empty] | 2016 |  |  |  | 2017
LABOR |  | EE Days | SE Days | Etech | Mtech | Machine Shop |  | EE Days | SE Days | ME | Etech | Mtech | Machine Shop |  | EE Days | SE Days | Etech |  | EE Days | SE Days | Etech
| Overall system design including benthic cable, underwater connectors, cable lay methods, etc. | 18 |  |  |  |  | Fabrication of battery connection manifold |  |  |  |  | 5 | 5 | System health and status monitoring | 5 | 5
| Detailed hardware design of instrument interfaces for 600 and 1200kHz ADCP's | 4 |  |  |  |  | Fabrication of battery system frame |  |  |  |  | 5 | 5 | Disassembly of battery spheres and installation of new batteries (swap 1) | 1 |  | 10 | Disassembly of battery spheres | 1 |  | 3
[7 empty] | Final fabrication | 5 |  |  | 5 | 5 |  | System pre-deployment testing | 5 | 5
| Set up and configure BIN testbed in lab. Testbed is used prior and during deployment. | 3 | 8 |  |  |  | System final testing | 5 | 5 |  |  |  |  | System deployment staging | 2 | 2
| Hardware and software integration of Acoustic Modem | 2 | 7 |  |  |  | System deployment staging | 2 | 2 |  |  |  |  | System deployment | 2 | 2
| Characterize sampling determinacy. Verify SIAM timestamp accuracy even in case of jitter. | 1 | 7 |  |  |  | System deployment | 1 | 1 |  |  |  |  | Disassembly of battery spheres and installation of new batteries (swap 2) | 1 |  | 10 | AUV MAPPING: |  | 10
| Software revisions to improve sampling determinacy | 1 | 17
| Coordinate acoustic instrument sampling | 1 | 6 | [14 empty] | BEDS TRACKING |  | 15
| Software to periodically retrieve internal instrument logs and store on BIN, clear instrument log memory | 1 | 7 |  |  |  | AUV MAPPING: |  | 10 |  |  |  |  | AUV MAPPING: |  | 10
| Software verification of data format and load path to SSDS |  | 2 |  |  |  | BEDS TRACKING |  | 15 |  |  |  |  | BEDS TRACKING |  | 15
| Software to periodically resynch instrument clocks with MOOS clock |  | 7
| Software for low-bandwidth health-status log for acoustic xmit |  | 5 |  |  |  | STEDS FABRICATION |  |  | 15
| BIN power energy budget verification testing | 1 | 1
| Detailed electrical hardware design of battery system | 10
| Documentation on battery handling procedures | 3
| Detailed mechanical design of battery system frame | 5 |  |  | 5
| Layout and fabrication of battery interface board | 1 |  | 10
| Detailed design of battery-BIN cable deployment system | 9
| Fabrication of battery-BIN cable deployment system |  |  |  | 5 | 10
| Detailed design of battery connection manifold | 5
| Assembly of battery spheres | 1 |  | 7
| Total (Days) | 66 | 67 | 17 | 10 | 10 | Total (Days) | 13 | 33 | 15 | 5 | 15 | 10 | Total (Days) | 16 | 39 | 20 | Total (Days) | 1 | 25 | 3
Expense | Battery manifold cabling and connectors (X2) | 4200 |  |  |  |  | Lithium batteries (2 packs) | 89944 | [5 empty] | Lithium batteries packs | 44972 |  |  | Li disposal Cost | 1387
| Battery mounting frame materials (X2) | 5900 |  |  |  |  | Cores (X50) | 3000 | [5 empty] | Li disposal Cost | 2774 |  |  | Decomissioning of instrumentation | 5000
| Frame fabrication Miscleaneous | 8000 |  |  |  |  | Grain Size analysis | 2500 | [5 empty] | sales tax | 3710.19
| Fabrication supplies | 9000 |  |  |  |  | Telemetry on STED's | 500 | [5 empty] | GENERAL SERVICE OF INSTRUMENTS (EST.) | 20000
| Benthos ATM-900-LF1 modem (X2) | 9000 |  |  |  |  | sales tax | 7900.24 | [5 empty] | SERVICING SUPPLIES | 5000
| Benthos ATM-900 transducer (X2) | 2990 |  |  |  |  | shipping | 1000 | [5 empty] | Telemetry on STED's | 500
| Upgrade memory storage (ADCP 300 KHZ) | 1000
| Upgrade Norteq aquadopp memory storage | 2550
| MOOS benthic releases fix | 11075
| Glass Spheres for 2 battery packs | 22008
| Batteries for testing, (one glass sphere contents) | 6929
| Sales tax | 6818.79
| Li disposal Cost | 214
| shipping | 500 |  |  |  |  | Sediment trap mooring and deployment hardware | 8500 | [5 empty] | Sediment trap mooring and deployment hardware (X2) | 17000 |  |  | Sediment trap decomissioning | 2000
| McLane Profiler Fix | 19500 |  |  |  |  | McLane profiler supplies and service | 5000 | [5 empty] | McLane profiler supplies and service | 10000 |  |  | McLane profiler supplies and service | 1000 |  |  | CCE Activity TOTAL
| Total | 109684.79 |  |  |  |  | Total | 118344.24 | [5 empty] | Total | 103956.19 |  |  | Total | 9387 |  |  | 341372.22
Shiptime | [6 empty] | WF | [6 empty] | WF |  |  |  | Decomissioning
[7 empty] | To deploy MOOS BIN, McLane profiler, sed trap + ADCP mooring at 1900m, STEDs deeper than 1,550m and recovery of J Barry mooring at 1300m | 5 | [5 empty] | Replace MOOS bin battery pack, recycle 1800 McLane profiler, recycle 1900 m mooring, and recover 1300 m mooring (X2) | 14 |  |  | WF
[7 empty] | Completion of deployments, Vibracoring and push coring before experiment official start | 3 | [9 empty] | Recover MOOS BIN, McLane profiler, 1800 m mooring, 1300 m mooring | 4
[7 empty] | Total WF | 8
[14 empty] | RC 10 hours |  |  |  | RC 10 hours
[7 empty] | RC 10 hours | [6 empty] | Deploy 1300 mooring, recycle 300 and 800 m mooring (X2) | 6 |  |  | Recover 300 m and 800 m mooring | 2
[7 empty] | Deploy STEDS and BEDS above 1300m depth, deploy USGS moorings at 330, and 800m, and J. Barry's at 1,300m | 8 | [5 empty] | ROV diving to search for BEDS and STEDS | 4 |  |  | ROV Search/recovery of BEDS and STEDS | 4
RC 24 hours
[7 empty] | AUV mapping at the beginning of the experiment and 1 month later, around MOOS BIN (1900m, around the STEDS and most of BEDS deployment areas, ( 100 m to 900m) | 4 | [5 empty] | RC 24 hours |  |  |  | RC 24 hours
[14 empty] | AUV mapping around MOOS BIN (1900 m), around the STEDS and most of BEDS deployment areas (100 m to 900 m) | 4 |  |  | AUV mapping at the end of the experiment, around MOOS BIN (1900m), around the STEDS and most of BEDS deployment areas, (100 m to 900 m) | 4
[7 empty] | PARAGON DAYS | 6
[14 empty] | PARAGON DAYS | 15 |  |  | PARAGON DAYS | 6
CAN BE MOVED TO ANOTHER YEAR PARTIALLY OR COMPLETELY
ADDED TO TOTAL COST IN THIS BUDGET MODIFICATION

## Additional cost 2014-2017 CCE
OTHER ACTIVITIES RELATED TO CCE BUT FUNDED THROUGH OTHER MBARI INTERNAL PROPOSALS
| 2014 |  | 2015 |  | 2016 |  | 2017
BEDS PROPOSAL | Current budget | 90270
| Fabrication 2 additional BEDS | 28000
J. BARRY PROPOSAL | Option 1: Fixing IRS sed traps
| Refit borrowed IRS traps | 5000
| Supplies for all traps | 6000
| Mooring Supplies (used with IRS or McLane Traps) | 4500
| Total | 15500
OR
Option 2: purchasing McLane Sediment traps
| Purchase 3 McLane Sediment traps | 73000
| Modify McLane traps for near-bottom use | 3000
| benthos floats | 4800
| misc mooring hardware | 5000
| Mooring Supplies (used with IRS or McLane Traps) | 4500
| Total | 90300
|  |  | Total | 0 | Total | 0 | Total | 0
CAN BE MOVED TO 2015 PARTIALLY OR COMPLETELY
[7 empty] | Total with IRS Traps | 133770
[7 empty] | Total with McLane traps | 208570
\

## OTHER ACTIVITIES 2014-PAULL
OTHER ACTIVITIES: BUDGET FOR 2014
| ACTIVITY 2, ARCTIC |  | ACTIVITY 3: Cruise SoCal w/Vrijenhoek's group |  | ACTIVITY 4: Ongoing Work |  | ACTIVITY 5 Statoil-Santa Monica Basin mapping | ACTIVITY 6: San Greogorio Fault Zone surveys |  | ACTIVITY 7: ROV sampling Monterey Canyon |  | OTHER
Expense | Rhizons | 3000 | Coring and sampling supplies | 3000 | Supplies Science | 5000 |  |  |  | Coring and sampling supplies | 3000 | AGU Attendance for 4 | 3090
| scintillation vials | 200 | ANALYSES |  | Upgrade computer | 6000 | [5 empty] | 8th International Gas-hydrate conference attendance for 1 | 3800
| labe tape | 50 | 14C forams | 6360 | 14C forams | 4240 |  |  |  | ANALYSES
| HPLC plasticware | 100 | foram wash for 14C | 360 | foram wash for 14C | 240 |  |  |  | 14C forams | 6360
| Miscelaneous (gas collection bags, syringes) | 300 | d18O, d13C CacCO3/sediment core | 750 | d18O, d13C CaCO3/sediment core | 1000 |  |  |  | foram wash for 14C | 360
| Shipping Gas canisters | 500 | DDT measurements | 4200 | d13C / d15N, % CaCO3 | 1000 |  |  |  | d18O, d13C CacCO3/sediment core | 500
| ANALYSES |  |  |  | DDT measurements | 2520 |  |  |  | d13C / d15N, % CaCO3 | 500
| 14C forams | 7950 | [7 empty] | Grain Size analysis | 625
| d18O, d13C CaCO3/sediment core | 500 | Travel to USGS for core logging | 1300 | [5 empty] | DDT measurements | 2800
| dC13, dD CH4 | 380 | Transportation from Southern California | 1200
| 14C CH4 | 750
| d18O, dD, H2O | 3750
| DDTr | 1680
| TOTAL | 19160 | TOTAL | 17170 | TOTAL | 20000 |  |  |  | TOTAL | 14145 | TOTAL | 6890
Labor |  | HOURS | [6 empty] | HOURS
| ME: GRAVES | 240
| SE: DAVE CARESS | 200 |  |  | SE: DAVE CARESS | 80 |  | SE: DAVE CARESS | 80
| EE: Sherman or Kacy | 240
| DMO-AUV: Thomas | 240
| DMO-AUV: Martin | 240
| ITD-Video support | 80
Shiptime | [7 empty] | RC: 24 hour-Days | 4 | WF, days | 14
[12 empty] | GRAND TOTAL OTHER ACTIVITIES | 77365