| 2015 Project Start Date: 01/02/15 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Total Resources for each resource category for all milestones listed here |
| --- | --- | --- | --- | --- | --- | --- |
| Milestone Date | 3/15/15 | 7/15/15 | 8/15/15 | 9/15/15 | 10/14/15 – 10/28/15 |  |
| Milestone Description | Battery system and BIN mounting frame designs complete | All battery spheres assembled and BIN system mounted on frame | BIN system instrument readiness review | All deployment hardware fabricated and assembled | Deploy BIN and moorings |  |
| EE | 137 | 137 | 20 | 5 | 5 | 304 |
| SE | 210 | 210 | 210 | 210 | 212 | 1052 |
| ME |  |  |  | 120 |  | 120 |
| EE Tech |  | 40 |  |  |  | 40 |
| SE Tech |  |  |  |  |  |  |
| ME Tech |  | 80 |  | 80 |  | 160 |
| Machine Shop |  | 60 |  | 20 |  | 80 |
| Divers |  |  |  |  |  |  |

This number should be the same number you entered on the resource requests for this particular resource.