Sedimentation Event Sensor

5Aug10

Management

• Update requirements docs (Paul)-done

• We will delay this project until 2011 due to other 2010 commitments.

• Set date for review, target sometime in Jan 2011 (Paul)

Electrical

• System interconnect diagram (Paul, Alana)-block diagram done, need schematic

• System schematics, including Controller, Fluor Cam, and Batt Sphere (Paul, Alana)

• Select and order EZ-Stepper drive (Paul)-received and tested by John

• Need to select cable types (Paul, Alana)

• Evaluate if MARS and deck cable ports can be combined on one Battery Sphere connecter

• Check Alana’s time on this project (Alana, Paul)

Mechanical

• Initial frame design (Brett)-done

• Initial fluorescence light design (Brett)-DSP&L light selected, need to make sure it will work in this application

• Select macro lenses (Brett, Paul) - stuck for now, will call Edmunds

• Sphere machining – in process (Brett)- three holes in hex hat, need to select final connectors (Paul)

• Mooring string design – (Ken)

Software

• Begin stripping down Rover code for SES (Rich, John) – this has started and is about half finished

• Write code for stepper motor interface (Rich, John) – 90% done

• Design and write mission behaviors (Rich, John)

• Get 4 GB card working with TS-7200 (Rich) - done

Key Dates

• MARS deployment scheduled on Pt. Lobos 4Oct10