## Sheet1
MBARI Status Update | 2023-12-19
Laser Ordered | 16 week Lead time | reaching out for best date for 1st laser
BOM/Procurement | in progress | Continuing on longer lead purchases - optical bench items
PCB's
| Controller Board | In house; fully functional
| Controller Daughter board | Ordered; in in about a week
| Power board/MCC | Functional so far
| Receiver board/with PD | In house; Fully functional
| Accelerometer board | In house; not tested
| Trigger Board | have in house available for bench setup when needed
| I/O Expansion Board | In review; not ordered; timing not critical
Housing | Design review 12/19
Software
| Data processing | alg date to RIAAT, data size is 1/6th - faster processing -
| Motor control scanning | 1-SPI interface to the motor control module defined and tested with simulated responses. SPI comm functioning; Motor spinning, hall feedback 2-Speed Control logic developed and ran several test scenarios: Alignment, Startup, open loop control, close loop control, coast and fault. Added laser pulse sync 3-Feedback loop is supported by digital hall effect encoders, using simple edge transitions for positional information. 4-Developed simple motor model and response for testing 5-Adding absolute motor encoder for position. Estimate completion this week.
| Data processing | Developed data processing update that applies data filters sooner and reduces amount of data that needs to be exchanged. Filters are for range and Intensity. Logic tested with simulation data responses. Code compiled but not yet integrated into hardware. Achieved the data reduction goals. Some logic to include some data points if nothing was detected in the asked for range limits and intensity limits so at least something is returned. Determined 18 bit sufficient for angular position
| Data Acquisition | Data acquisition separated from how data is processed.
| Prototype Logic | Prototype logic for updating a large number of averages and saving data between collections. This is applicable to how the collection of temperature data will need to be done.
| Next from Nov14th | 1-Putting software on the updated daughter card, testing motor speed control - positional accuracy/repeatability/stability. Configuration settings, motor startup and shutdown. In progress 2- Laser - detector signal capture, positional marking, testing positional accuracy/precision/stability/Quality. Could start with 40 Khz older laser, but really want the new laser information, especially for data rate. 3-Temperature - detector signal capture, binning/averaging, merging of data into scan information data stream.
December update date?
integration and timing with MBARI | TBD
June 3-5
order bulkheads/schematics | complete
final pinout - have from
next review dec 19 + housing review | complete
to provide updated slides with actions from Mike S.