## Sheet1
MBARI Status Update | 2024-03-26 | Sensor Target Date TBD, 2024; review schedule so available June 3
Laser Ordered |  | Achieving power spec - To be sent after burn it
BOM/Procurement | in progress | Continuing on longer lead purchases - longest leads ordered, AR coating time?
PCB's
| Controller Board | In house; fully functional | complete
| Controller Daughter board | Ordered; in in about a week | complete
| Power board/MCC | Functional | complete
| Receiver board/with PD | In house; Fully functional | complete
| Accelerometer board | In house; not tested | complete
| Trigger Board | have in house available for bench setup if needed | TBD | should not be needed - needs to be proved
| I/O Expansion Board |  | complete
Housing
| deterimine 22 inch tube | Mike/nelson - Mike to send model 2/28 | complete
| pcb mounting etc.. | Mike -next weeks | in progress
| window protector | Mike | Prelim complete | reviewwith MBARI
Optical Bench |  | To build when parts on in
| Red wavelength test | Jon | in progress | red filters and mounts here
| Specs for Window and order | Jeff/Brian/Carl | complete
| Back Reflection Test | Jeff/Mike/Russ | complete
Electrical | over all power calc DC/DC review | Nelson - best calcuation for power and update Eric | in progress | with laser
| Motor power supply review | Nelson/Tom - motor friction has decreased | in progress
| SW linear att | Dom | 10%
| Laser control | Dom (when laser is here) | start next week
Software
| Motor Control/Position |  | 90 %in progress
1 | Encoder |  | complete | functional
| Data Collection - initial Scan |  | 80%
| Data Processing |  | 50%
2 | GUI/RTV/Display/ - Upgrades |  | 95%
5 | Accelorameter SW/test |  | 0%
6 | low power state |  | 0% | to define
| integrate linear motion SW/Test |  | 0%
3 | photo det - digital pot control |  | 0%
7 | TEC control - |  | 0% | Manually functions
| Raman SW |  | 50%
Action Items to work through: front cover/shrowd protector - to update, 4000m vs 6000 m choice, pins in the end moved to bracket
Cables and connectors being looked at
Presure testing