## short
Biggest issue in Completing Insert - in progress | then to test with window bottle closed, calibrations
| last update | 2025-02-25 |  | Additional Comment
MBARI Computer | Here today | Good | thank you!
PO | Complete | Complete | thank you!
Moved Return and Trigger to different channels to improve startup power setting | Complete | Complete | completed 2/11 - improved; functional
Range Precision | Complete | Complete | meets specification 2mm
Angle Resolution |  |  | excellent; to measure again at later time
Insert Bonding | In progress | In progress | final window with insert 1 to 2 days | today - took longer
Build up fit test | In progress | Complete
Continuing on Functionality; I2C, Spi, Bias | In progress | Complete
Calibration - internal plan, Range precision | In progress | In progress | plenty to do
Temperature tested | not yet started | Complete |  | complete
SIT | not yet started | not yet started
MBARI Items: (change from last time) | Targets
Rx TEC |  | NA | Functional but may not be required
MCC temperature monitoring mod - two resistors and test |  | Complete | Functional
FEA updated window - as it changed a bit |  |  | Complete
Bond Final window | 2025-01-17 | In Progress | Complete adding insert
Scan testing with Updated Window | 3rd week Jan | Complete | completed last time
Update Optical Bench with two new parts | early next week | Complete | Complete; all final optical bench items complete; fit was complete, two items being anodized
Scan testing with Updated Window bottled |  | not yet | Target end of this week - risk; early next week
Start Advanced Calibrations - background subtractions |  | TBD if required | Started
Pressure Test | End of month | Complete | Complete
Thermal Sensing - have not gotten back to POC - order of operations of the math | end of month.. | In progress | aligning Red channels later this week
Accelerometer | not sure yet | In progress | to test this week - very basic
Longmont SIT - Date TBD |  | March
Date TBD (late Feb/early March?) - MBARI Tank Test | TBD | March
April 01? Subsea test with MBARI (Can not move) | TBD | Risk | No change
Laser on at 9% power: 2.65A | 24Volts | 63.6 | watts | low speed motor
Laser on at 100% power: 3.18A | 24Volts | 76.32 | watts | low speed motor
2.08 amp without laser