## Sheet1
MBARI Status 6/8/2023
1 | Believe we can Accommodate Critical design Review | Mind July | Must run past carl, specific dates TBD; <Late July complete Critical Design Review and other factors; mid July good
2 | POC - if desired Temp Sensing | 2 Months - don't know lead times | May be able to get it in < Critical Design Review; have many of the components; needs to be costed/schedule Filters needed for sure, may be able to use in house lasers but not at range desired; Bench Test TBD more confort - level of comfort - can scope and schedule
3 | Schedule Date Constraints needed | Eric mentioned Due dates to be maintained; please elaborate | Critical Design Review; - Delivery Date, FAT; Quote Cost full proposal to build - Date - week after CDR
4 | Can update Schedule for next week |  | Yes for next week 6/12
2 - DETAILD DESIGN AND CRITICAL DESIGN REVIEW
2a - Optical Components
| Laser - Green | Identifying, cost prohibitive so far | what is the level of concern from Carl
| TX Lens Design | Complete
| Receiver Design | Complete | Functional, to tweek BW on electronics; good photodetector
| Window | Complete
| Prism/Mirror | Complete
| Corrector Lens | Complete | May need to update for Temp sening Filters but not difficult
| Temperature Sensing Optical Design | Design In progress | Consider POC if something more tangible is required in short term. Has not been costed. Date for POC TBD - 2 Months?
2b - Optical Bench
| Optical Mechanical Design | Complete
2c - Mechanical Design
| Design | Complete
| Internal Design review | Complete
| Procurement | TBD | Need to review all parts
| Window Bonding Experiments | Complete
| Design Modifications/Bonding Documentation | 90% | Production Engineer/Man has reviewed and updated
| Buildup Tube and window for Pressure Test | Complete
| Pressure Test Equipment Procurement | Complete
| Housing Design | Complete
| Bulk Head Feedthrough connectors | Should be good but need to check | We talked about connectors before..
Internal Design/Integration
| Scanner Mount Design | Complete
| Motor Identification | Complete
| rotating Shaft | Complete
| Mirror to Shaft connection | Complete
| Rotation Testing -Balance testing, etc. | Complete
| Optical Bench Design | TBD
| ME PCB Chassis Design | 60%
| Thermal Cooling Design | conceptual only | needs work
| Power Board Mount | conceptual only | needs work
| Laser Mount | conceptual only | needs work
| Photodetector Mount | conceptual only | needs work
| Trigger Board Mount | conceptual only | needs work
| CMD/RD BK PCB Mount | conceptual only | needs work
2d - Electronics
| Trigger Board - consolidate Existing Design | 60% | to update and consolidate existing Design, update front end
| Power Board | 80% | to add DCDC from 18-36 V to 48V or 36V
| Receiver Control | Complete | Functional, in house, to consolidate and turn
| Digitizer/Controller Board Updates | Complete | Added I/Os for Temp Sensing, current in house hardware can be used to test
| Motor Controller | 95% | Not ordered, Tested with Eval board
| Temperature Sensing Electronics Design | 100% | Design Complete
2e - Software
| Thermal Sensing Software Design | 60%
| Hollow Core Motor Control/New Scanner | 30% | Just spin test and confirmed speed
| Calibration Tools | 0%
| CCI | 80% | Dynamic Laser control still needed
| Data formats and deliverables | 50%
| Automatic Gain Control Variable Attenuator1 | 0%
| Trigger Variable Attenular Implementation | 0%
| PTP | not required
| Real Time Viewer - for thermal data display | 0%
| 2f - Cable Harness/Anode Protection/Cable Routing | Not Started
| 2g - Integration Assembly | 50%
| 2h - Production Readiness / Documentation | 10%
Actions:
Finalize CDR date < June29th
provide feedback on Laser
| For Review: during the CDR :Get overview of company | number of offices and what they do