## Sheet1
Notes
Dinner 7/26 with MBARI
| MBARI Status 7/18/2023 |  | Actions/Comments
1 | Critical design Review | July 27,2023 | Send Slides to Eric end of day 7/25 Provide Dave with updated Cost estimate 7/25; with and w/out 2nd Laser; cost of 2 vs individual 7/26 - dinner CDR < presentation, schedule, estimate cost Business Casual
2 | Temp Sensing |  | higher risk - focus on narrative on why it should work | Since high risk provide design basis to supprot why this feature should work
2 - DETAILD DESIGN AND CRITICAL DESIGN REVIEW
2a - Optical Components
| Laser - Green | Complete | $35k; suggest purchasing two | What is the life of the Laser?
| TX Lens Design | Complete |  | Can we have more than 12 month warranty for the laser?
| Receiver Design | Complete | Functional, to tweek BW on electronics; good photodetector | Warranty from 3D at Depth?
| Window | Complete
| Prism/Mirror | Complete
| Corrector Lens | Complete | May need to update for Temp sening Filters but not difficult
| Temperature Sensing Optical Design | Complete | Consider POC if something more tangible is required in short term. Has not been costed. Date for POC TBD - 2 Months?
2b - Optical Bench
| Optical Mechanical Design | Complete
2c - Mechanical Design
| Design | Complete |  | Outline Model for Dave 7/25 - cable length - ME engineer
| Internal Design review | Complete
| Procurement | See Comment | With Approval | MBARI may look at Authroity to proceed < Sept 1
| Window Bonding Experiments | Complete
| Design Modifications/Bonding Documentation | 90% | Production Engineer/Man has reviewed and updated
| Buildup Tube and window for Pressure Test | Complete
| Pressure Test Equipment Procurement | Complete
| Housing Design | Complete
| Bulk Head Feedthrough connectors | Complete | updated
Internal Design/Integration
| Scanner Mount Design | Complete |  | available design for integration approx Feb 24
| Motor Identification | Complete
| rotating Shaft | Complete
| Mirror to Shaft connection | Complete
| Rotation Testing -Balance testing, etc. | Complete
| Optical Bench Design | TBD
| ME PCB Chassis Design | Complete
| Thermal Cooling Design | conceptual only
| Power Board Mount | conceptual only | needs work
| Laser Mount | conceptual only | needs work
| Photodetector Mount | conceptual only | needs work
| Trigger Board Mount | conceptual only | needs work
| CMD/RD BK PCB Mount | conceptual only | needs work
2d - Electronics
| Trigger Board - consolidate Existing Design | 80%
| Power Board | Complete | to add DCDC from 18-36 V to 48V or 36V
| Receiver Control | Complete | Functional, in house, to consolidate and turn
| Digitizer/Controller Board Updates | Complete | Added I/Os for Temp Sensing, current in house hardware can be used to test
| Motor Controller | Complete | Not ordered, Tested with Eval board
| Temperature Sensing Electronics Design | Complete | Design Complete
2e - Software
| Thermal Sensing Software Design | 60%
| Hollow Core Motor Control/New Scanner | 30% | Just spin test and confirmed speed
| Calibration Tools | 0%
| CCI | 80% | Dynamic Laser control still needed
| Data formats and deliverables | 50%
| Automatic Gain Control Variable Attenuator1 | 0%
| Trigger Variable Attenular Implementation | 0%
| PTP | not required
| Real Time Viewer - for thermal data display | 0%
| 2f - Cable Harness/Anode Protection/Cable Routing | Not Started
| 2g - Integration Assembly | 50%
| 2h - Production Readiness / Documentation | 10% |  | Need length of 13 pin cable from MBARI; Eric