## Sheet1
|  |  | Labor (Hours) | [7 empty] | Material | Outside Srv | Sub-totals |  | Notes
Task |  |  | Hamilton | Bird | ME | Martin | EE | ME Tech | EE Tech | Machinist |  |  | Expense | Labor
New Sled Design and Buid - Jobbed out
| Design |  | 24 | 24
| Fabrication |  | 8 | 8 |  |  |  | 8 |  |  |  | 20000 |  |  | Costs based on MRS sled build.
Task Total |  |  | 32 | 32 | 64 | 0 | 0 | 8 | 0 | 0 | 0 | 20000 | 20000 | 72
Instrument Frame Design and Buid
| Design |  | 20 | 20
| Fabrication |  | 20 | 80 |  |  |  | 40 |  |  | 2000 | 2000 |  |  | ROM Estimate on Costs
Task Total |  |  | 40 | 100 | 140 | 0 | 0 | 40 | 0 | 0 | 2000 | 2000 | 4000 | 180
Hydraulics Design and Integration
| Design |  | 16 |  |  | 24
| Source Rams |  | 8 | [7 empty] | 5000 |  |  |  | ROM Estimate from Hydratech
| Source Valves |  | 8 |  |  | 8 |  |  |  | 16 | 6000 |  |  |  | ROM Estimate on Costs
| Souce Plumbing |  | 8 | [7 empty] | 3000
| Integration |  | 16 | 16 |  | 24 |  | 20
Task Total |  |  | 56 | 16 | 72 | 56 | 56 | 20 | 0 | 16 | 14000 | 0 | 14000 | 164
Software Integration
| Tilt Sensor Integration w/ Ricketts |  |  |  |  | 8
| Hydraulic Valve Integration w/ Ricketts |  | 8 |  |  | 16 |  |  | 8
| Tilt-A-Sled Modifications for Ricketts |  | 8 |  |  | 16
Task Total |  |  | 16 | 0 | 16 | 40 | 40 | 0 | 8 | 0 | 0 | 0 | 0 | 64
At Sea Test
| Two Days |  | 24 | 8 |  | 24
Task Total |  |  | 24 | 8 | 32 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 56
|  |  | Labor (Hours) | [7 empty] | Material | Outside Srv
[5 empty] | ME |  | EE | ME Tech | EE Tech | Machinist
Totals |  |  | 168 | 156 | 324 | 120 | 120 | 68 | 8 | 16 | 16000 | 22000 | 38000 | 536
[5 empty] | 324 |  | 120 | 68 | 8 | 16 |  |  | 38000 | #REF!
2016 Totals |  |  | 392 | 396 | 1104 | 156 | 512 | 340 | 202 | 136 | 47000 | 7400 | 62400 | 2730
Milestone
| 1 | 1st Deploy | 44 | 24 |  | 28 |  | 14 | 0 | 8
| 2 | Power+Battery | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
| 3 | 2nd Deploy | 44 | 24 |  | 28 |  | 14 | 0 | 8
| 4 | LRI Report | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
| 5 | Winter Deployment | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
[8 empty] | #REF! | #REF! | #REF! | #REF!
Alternate
New Sled Design and Buid
| Design |  | 24 | 24
| Fabrication |  | 8 | 60 |  |  |  | 60 |  |  | 5000 | 5000 |  |  | Material+HeatTreat
Task Total |  |  | 32 | 84 | 116 | 0 | 0 | 60 | 0 | 0 | 5000 | 5000 | 10000 | 176
|  |  | Labor (Hours) | [7 empty] | Material | Outside Srv
[5 empty] | ME |  | EE | ME Tech | EE Tech | Machinist
Totals |  |  | 168 | 208 | 376 | 120 | 120 | 120 | 8 | 16 | 21000 | 7000 | 28000 | 640
Alternate
Re-Use MRS Sled
| Design |  | 16 | 16
| Fabrication |  | 8 | 16 |  |  |  | 20 |  |  | 2000
Task Total |  |  | 24 | 32 | 56 | 0 | 0 | 20 | 0 | 0 | 2000 | 0 | 2000 | 76
|  |  | Labor (Hours) | [7 empty] | Material | Outside Srv
[5 empty] | ME |  | EE | ME Tech | EE Tech | Machinist
Totals |  |  | 160 | 156 | 316 | 120 | 120 | 80 | 8 | 16 | 18000 | 2000 | 20000 | 540