## Slide 1: Self-Contained Plankton Imager Overview
Tuesday Nov 6 2012

## Slide 2: What is SCPI?
Differs from existing systems which are:
  Require dedicated cables, ships, and winches
  Difficult to deploy, maintain, and operate
  High cost
Widely distributed

## Slide 3: SCPI Users and Use Cases
Users
Steve Haddock
Ken Smith
Jim Bellingham
CANON
Platforms
AUVs
Profilers
Moored (Plankton Vane)
Sediment Traps
Observatory (Cabled Option)
Manually dropped or towed
Ships of opportunity
Pier mounted

## Slide 4: Where are we now?
Completed camera assessment (March 2012)
Completed light quantification requirements (April 2012)
Conducted a Concept Design Review (May 2012)
Battery housing fabricated (August 2012)
LED housing fabricated (September 2012)
LED circuit board fabricated (September 2012)
NiMH battery packs on order (October 2012)
The software is 90% complete (tested on a prototype control board).
LED driver board in final layout (October 2012)
Camera control board in final layout (November 2012)
Camera housing in final design (November 2012)
Spare housings and end caps fabricated (October 2012)
Connectors and cables due (October 2012)

## Slide 5: Camera Module
insert mech drawing of cam module

## Slide 6: LED Module

## Slide 7: Battery Module
insert mech drawing of batt module

## Slide 8: Where will we be at the end of 2012
Complete protoype
Bench testing
Test tank testing

## Slide 9
Meets requirements of:
LaGrangian Sediment Trap (Smith Lab)
Macro Zooplankton (Haddock Lab)
This prototype will allow:
Testing of modular concept
Testing of image quality in real world conditions under various light levels
Testbed for higher image quality SCPI system

## Slide 10: Proposed schedule for 2013
1st Quarter: Perform multiple field tests
2nd Quarter: Develop higher image quality camera module based on test results
3rd Quarter: Build two complete SCPI systems
4th Quarter: Testing and deployment

## Slide 11: Where does SCPI fall within MBARI Camera Projects?
COST
SIZE
Shark Cam
SCPI
Imaging AUV
Ocean Imaging
Time-Lapse
Camera
Moored
Camera Sys
LRAUV
Verification Cam

## Slide 12: Relevance to Strategic Plan
Research Themes: Ocean Visualization
  SCPI allows for realizing four-dimensional visualizations – repeated spatial renderings over time.
Institutional Objectives: (2) Increase Institutional Flexibility
  Rapid prototype
Institutional Objectives: (3) Enhance Collaborations
  Low cost of SCPI eases ability of outside organizations to build their own, thus increasing the spatial network

## Slide 13: End

## Slide 14: Science Motivation
Macroplankton Quantification
  Physical Sensors: relatively easy. “Biology” = fluorometry
  Increase spatial coverage and time series
Sedimentation and marine snow flux
Ground-truthing acoustical biomass
Reconfigurable target size via optics
Primary users: MBARI principal investigators
Affordable for cities, individuals & small institutes
Widely available for diverse applications
Uses:
Users:

## Slide 15: How is it Different?
Many existing systems
  All “Oceanographic” scale
  Requires dedicated cables, ships, and winches
  Packages difficult to deploy, maintain, and operate
  High cost
Crittercams
  Not available for plankton-sized targets

## Slide 16: Low-Cost, Widely Distributed
Off the shelf parts
  Available online or locally
Low cost
  Total system cost <$3000
Easy to manufacture
Open source
  Meets needs of MBARI PIs first
  All schematics, software, plans posted on web

## Slide 17: Deployment Modes
AUVs
Profiling
Moored (Plankton vane)
Sediment traps
Observatory (Cabled option)
Manually dropped or towed
Ships of opportunity
Pier mounted

## Slide 18: Modular Functionality
Camera
Light
Light
Battery

## Slide 19: Example of 6x40 degree Conical Reflector (Red is common volume between imager and light field)