## Sheet1
MINI ROV UPGRADES
Item | Detail | M Tech | E Tech | M Eng | E Eng | Mch Shop |  | Materials
Manipulator |  | 120 | 0 | 260 | 64 | 160 |  | 43000
| Spec and purchase |  |  | 20 |  |  |  | 40000
| Arm and can brackets | 40 |  | 40 |  | 40 |  | 500
| Drawer motor |  |  | 80 |  | 80 |  | 1500
| Install/integration/test | 40 |  | 40 | 40
| Tube core/sampling devices | 40 |  | 80 |  | 40 |  | 500
| Misc hardware/connectors |  |  |  | 24 |  |  | 500
Control van |  | 120 | 56 | 40 | 16 | 0 |  | 24250
| 20' x 8' bare container |  |  | 40 |  |  |  | 4050
| Insulation & walls | [6 empty] | 4100
| Electrical/lighting/heating | 40 | 40 |  |  |  |  | 6500
| Personel doors | [6 empty] | 1500
| Electrical pass thru | [6 empty] | 1500
| Misc hardware | [6 empty] | 300
| shipping | [6 empty] | 800
| Work bench/tool cabs | 80 | [5 empty] | 5500
| ROV topside installation |  | 16 |  | 16
Neutral Umbilical |  | 40 | 40 | 40 | 40 | 0 |  | 30000
| Spec and purchase |  |  | 20 | 20 |  |  | 30000
| Install/integration/test | 40 | 40 | 20 | 20
Midwater Samplers |  | 140 | 24 | 310 | 80 | 160 |  | 15000
| Sampler index motor |  | 24 | 80 | 80 | 40 |  | 2000
| Suction pump motor |  |  | 40 |  | 40 |  | 2000
| sampler mech | 80 |  | 110 |  | 80 |  | 5000
| Detritus sampler | 40 |  | 40
| D-sampler door open/cls mech | 20 |  | 40 |  |  |  | 5000
| Misc hardware/connectors | [6 empty] | 1000
Vehicle Improvements |  | 180 | 100 | 448 | 388 | 240 | 0 | 43800
| Focal upgrade | 20 | 40 | 24 | 24 | 20 |  | 3300
| Update Epod housing | 20 |  | 80 | 40 | 60 |  | 2000
| Update umbilical j-box | 20 |  | 40 | 20 | 40 |  | 500
| Fiber connectors upgrade |  |  | 24 | 24 |  |  | 18000
| Power upgrade | 40 | 40 | 120 | 120 | 80 |  | 10000
| Winch level wind | 80 | 20 | 160 | 40 | 40 |  | 10000
| Improve documentation |  |  |  | 40
| Power system optimization |  |  |  | 80
Annual Maintenance/spares/consumables budget |  | 80 | 80 | 80 | 80 | 80 |  | 15000
|  | 80 | 80 | 80 | 80 | 80 |  | 15000
Totals |  | 680 | 300 | 1178 | 668 | 640 |  | 171050