## Sheet1
MINI-ROV 2014 TO DO LIST
| Priority | Owner
New Items
Identify new video recorder | 1 | Alana/Dale
Video overlay | 2 | Dale
Integrate new tether | 1 | Alana/Dale
Level wind for winch | 1 | Dale
Build spare vicor can | 1 | Alana/Dale
Belly pack | 2 | Alana/Dale
Dive log database | 1 | Dale
Sampling drawer | 1 | Dale
add wires for vicor shut off | 1 | Alana
Test EPOD |  | Alana
build up spare thrusters
design brackets for manip epod
Submit drawer motor to shop
finish drawer assembly design
test shared variables
test teradek
switch stbd vert/horizontal
verify I/O map
move elmo files to raid drive
install composer onto win 7 laptop
Tune level wind motor
program level wind drive
tune & program spare thrusters
comp vicor can and install
finish wiring winch jbox
test sheave counter
Upgrades
Sonar housing | 1 | Alana
Replace control van computers | 1 | Dale
Move over to new power supply | 1 | Alana
Hook up EPOD voltage divider | 2 | Alana
Software upgrades | 1 | Dale
Maintenance
DVL cold room test | 2 | Alana
Repair winch shaft | 1 | Dale
repair winch control box | 1 | Alana
Make new bushings for lift frame | 1 | Dale
Modify lift bail for easier removal | 1 | Dale
Modify main j-box mounts | 2 | Dale
Fix tilt motor endcap |  | Dale
Modify toolsled mounts |  | Dale
Need to Buy
Spare winch motor
Video overlay box
Belly pack components
Level wind motor and lead screw
New winch nema box
Sonar housing
Spare computer
Spare for manipulator
Connectors for spare vicor can |  | Alana | X
Littelfus GFI module |  | Alana
Rackmount monitor
Spare DSPL light (5000 lumens)