## Sheet1
2017 Midwater cruise prep. (Cruise date = 2/2/2017)
O2 Sensor/DGH Can build |  |  | Alana | Dale | Frank | Mike P | Larry | Tom | Jim | Jose
| strip and plate housing |  |  | X
| wire up new DGH module | [6 empty] | X
| complete software for reading DGH sensor and displaying |  |  | X
get O2 sensor calibrated/replaced
|  | checking with Erich R. |  | X
| cabling for DGH can, pump and O2 sensor |  | X |  |  |  |  | X
| schematics |  | X
Pump motor build
| assemble thruster |  |  | X
| tune motor |  |  | X
print shroud/prop?
| wire j-box w/filter board and vicor board |  | X |  |  |  |  | X
| schematics |  | X
| mold up cable assembly (mink-8L to mink 8L) |  | X | X |  |  |  | X | X
| order MINK-8L-BCR |  | X
| modify small prop | [5 empty] | X
| Find MINK-8L-CCP inserts |  |  | X
| add anode port on elmo housing | [5 empty] | X
| software for pump control (add to index .exe) |  |  | X
| design shroud post |  |  | X
| machine shroud posts | [5 empty] | X
Build up new j-box (micro board)
| order subconn connectors |  |  | X
MCBH8F (8)
MCBH4F (4)
MCBH2F (2)
| build up regen board & test |  | X
| add mounting holes for second vicor |  |  | X
| order 48 to 24vdc vicor |  | X
| make orings up for lid and base |  |  |  | X
| wire up micro and cable assembly |  | X |  |  |  |  | X
Build up new carousel index motor assembly
| order subconn connectors |  |  | X
MCBH8F (2) 1/2 Thread length
MCBH6F - 1/2 Thread length
| order spare motor controllers |  |  | X
| schematic |  | X
| mount for index camera |  |  | X | X
| complete pcb for controller |  | X | [6 empty] | X
| modify maxon gear shaft |  |  |  |  | X
Build up new toolsled skid
| mount carousel frame |  |  |  | X
| mount DVL | [5 empty] | X
| add stiffners to the top rails |  |  |  | X
| fix slides (won't slide now) |  |  |  | X
| Bracket for O2 and pump |  |  |  | X
| compensator bracket (2 units) |  |  |  | X
| mounting posts for J-box |  |  |  | X
| bracket for DGH can |  |  |  | X
| mount comp manifold |  |  |  | X
Completed
In process