## Sheet1
Item/Detail | M Tech | E Tech | M Eng | E Eng | Mch Shop |  | Materials
Manipulator | 120 | 20 | 260 | 64 | 160 |  | 43000
Spec and purchase |  |  | 20 |  |  |  | 40000
Arm and can brackets | 40 |  | 40 |  | 40 |  | 500
Drawer motor |  |  | 80 |  | 80 |  | 1500
Install/integration/test | 40 |  | 40 | 40
Tube core/sampling devices | 40 |  | 80 |  | 40 |  | 500
Misc hardware/connectors |  |  |  | 24 |  |  | 500
Control van | 120 | 56 | 40 | 16 | 0 |  | 34250
20' x 8' bare container |  |  | 40 |  |  |  | 6050
Insulation & walls | [6 empty] | 6100
Electrical/lighting/heating | 40 | 40 |  |  |  |  | 8500
Personel doors | [6 empty] | 3500
Electrical pass thru | [6 empty] | 3500
Misc hardware | [6 empty] | 300
shipping | [6 empty] | 800
Work bench/tool cabs | 80 | [5 empty] | 5500
ROV topside installation |  | 16 |  | 16
Neutral Umbilical | 40 | 40 | 40 | 40 | 0 |  | 30000
Spec and purchase |  |  | 20 | 20 |  |  | 30000
Install/integration/test | 40 | 40 | 20 | 20
Midwater Samplers | 140 | 24 | 310 | 80 | 160 |  | 15000
Sampler index motor |  | 24 | 80 | 80 | 40 |  | 2000
Suction pump motor |  |  | 40 |  | 40 |  | 2000
sampler mech | 80 |  | 110 |  | 80 |  | 5000
Detritus sampler | 40 |  | 40
D-sampler door open/cls mech | 20 |  | 40 |  |  |  | 5000
Misc hardware/connectors | [6 empty] | 1000
Vehicle Improvements | 180 | 100 | 448 | 388 | 240 | 0 | 43800
Focal upgrade | 20 | 40 | 24 | 24 | 20 |  | 3300
Update Epod housing | 20 |  | 80 | 40 | 60 |  | 2000
Update umbilical j-box | 20 |  | 40 | 20 | 40 |  | 500
Fiber connectors upgrade |  |  | 24 | 24 |  |  | 18000
Power upgrade | 40 | 40 | 120 | 120 | 80 |  | 10000
Winch level wind | 80 | 20 | 160 | 40 | 40 |  | 10000
Improve documentation |  |  |  | 40
Power system optimization |  |  |  | 80
Annual Maintenance/spares/consumables budget | 80 | 80 | 80 | 80 | 80 |  | 15000
| 80 | 80 | 80 | 80 | 80 |  | 15000
Totals | 680 | 320 | 1178 | 668 | 640 |  | 181050