300080  DMO  Support      Mini ROV 

Current status of project and results to date

The MiniRov is on track to complete approximately 26 dives in 2015, which included operations in the GOC , Rachel Carson , external vessels, and the MBARI test tank.  

2015 was the first year that engineering support labor was tracked within DMO support project. Note these resource numbers do not track labor for ROV operations.

Engineering labor status to date is as follows- 

EE was budgeted for 200 and used 76
Etech was budgeted for 0 and used 21
Graves was budgeted 250 and used 131 
Mtech was budgeted 0  and used 166
SE  was  budgeted 60 and used 0  ( Engineer  was not available  to participate)





 
Significant changes from previous project proposal 

In 2016 the Mini ROV is scheduled to be used for an ARTIC expedition, in addition to operations in Monterey Bay on MBARI vessels, test tank, and external vessels. Operating labor requests for this platform will come from the respective science projects. Upgrade, maintenance and repair labor will be addressed within this DMO support project.

Scheduling of the Mini ROV activity will be centered on the June to November Artic shipping schedule. Any engineering and scientific dives will have to be focused for the first part of the year. 

Three days of Rachel Carson will be requested for offshore testing of the Mini ROV. If the Carson is oversubscribed this activity can be moved to an external vessel if appropriate funding
is provided . These operations will be targeted for May 2016, to allow enough time for development.


Proposed upgrades (which were proposed at the abstract phase) to this platform include the following:

1. Data Sharing /Precision controls 
2. Data Logging and Archiving 
3. Video annotation
4. Core System maintenance.


 Based on input from D. Graves we are requesting the following resources:

Increase to 250  A. Sherman 
Increase to 400 D. Graves 
Increase SE ( Schilling) to 200 hours ( task 3)
Increase SE ( Schram ) to 200  hours ( task 2 )
Increase Etech to 80
Increase Mtech to 200
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