## Labor Hours
Labor_Category by Time | Jan-2023 | Feb-2023 | Mar-2023 | Q1-FY23 | Apr-2023 | May-2023 | Jun-2023 | Q2-FY23 | Jul-2023 | Aug-2023 | Sep-2023 | Q3-FY23 | Oct-2023 | Nov-2023 | Dec-2023 | Q4-FY23 | FY2023 | Jan-2024 | Feb-2024 | Mar-2024 | Q1-FY24 | Apr-2024 | May-2024 | Jun-2024 | Q2-FY24 | Jul-2024 | Aug-2024 | Sep-2024 | Q3-FY24 | Oct-2024 | Nov-2024 | Dec-2024 | Q4-FY24 | FY2024 | Jan-2025 | Feb-2025 | Mar-2025 | Q1-FY25 | Apr-2025 | May-2025 | Jun-2025 | Q2-FY25 | Jul-2025 | Aug-2025 | Sep-2025 | Q3-FY25 | Oct-2025 | Nov-2025 | Dec-2025 | Q4-FY25 | FY2025 | Jan-2026 | Feb-2026 | Mar-2026 | Q1-FY26 | Apr-2026 | May-2026 | Jun-2026 | Q2-FY26 | Jul-2026 | Aug-2026 | Sep-2026 | Q3-FY26 | Oct-2026 | Nov-2026 | Dec-2026 | Q4-FY26 | FY2026
Allen, Jerry - 0667 | [12 empty] | 2 |  |  | 2 | 2 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beebe, Christopher - 1276 | [21 empty] | 46 | 28 | 1 | 75 |  |  | 13 | 13 |  |  |  |  | 88 | 7.5 | 6 | 5 | 18.5 | 8 |  |  | 8 | [8 empty] | 26.5
Coenen, Paul - 0491 | [18 empty] | 1 |  | 1 | [12 empty] | 1 |  |  |  |  | 3 |  |  | 3 | [8 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flores, Frank - 0461 | 53 | 88 | 123 | 264 | 142 | 85 | 44 | 271 | 36 | 108 | 27 | 171 | 93 | 81 | 36 | 210 | 916 | 27 | 63 | 102 | 192 | 88 | 99 | 54 | 241 | 45 | 45 | 44 | 134 | 86 | 114 | 36 | 236 | 803 | 97 | 80 | 113 | 290 | 124 | 27 |  | 151 | [8 empty] | 441 | 26.6667 | 26.6667 | 26.6667 | 80 | 26.6667 | 26.6667 | 26.6667 | 80 | 26.6667 | 26.6667 | 26.6667 | 80 | 26.6667 | 26.6667 | 26.6667 | 80 | 320
Hernandez, Yamir - 1265 | [19 empty] | 35 | 35 | 19 | 7 | 40 | 66 | [8 empty] | 101 |  |  |  |  | 5 |  |  | 5 | [8 empty] | 5
Jansen, Benjamin - 1317 | [36 empty] | 5 | 5 | 4 | 4.5 |  | 8.5 | [8 empty] | 13.5
Kecy, Chad - 0758 | [22 empty] | 10 |  | 10 | [8 empty] | 10
McClure, James - 1167 |  |  | 1 | 1 | 32.5 | 6 |  | 38.5 |  | 6.5 | 28 | 34.5 | 8 | 2.5 |  | 10.5 | 84.5 |  | 0.5 |  | 0.5 |  | 2 |  | 2 |  |  | 1 | 1 |  | 2 | 5.5 | 7.5 | 11 | 3.5 |  |  | 3.5 | 11 | 0.5 |  | 11.5 | [8 empty] | 15 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 160
Montgomery, James - 0754 |  |  | 3 | 3 | [12 empty] | 3 |  |  |  |  | 2 |  |  | 2 | [5 empty] | 1 |  | 1 | 3 |  |  |  |  | 2 |  |  | 2 | [8 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rosal, Jose - 0591 | [39 empty] | 4 |  | 4 | [8 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sherman, Alana - 0590 | 13 | 36 | 113 | 162 | 89 | 49 | 20 | 158 | 8 | 28 | 53 | 89 | 82 | 50 | 29 | 161 | 570 | 16 | 22 | 30 | 68 | 22 | 16 | 5 | 43 | 17 | 13 | 25 | 55 | 33 | 61 | 16 | 110 | 276 | 29 | 30 | 39 | 98 | 72 | 25 | 8 | 105 | 12 |  |  | 12 |  |  |  |  | 215 | 30 | 30 | 30 | 90 | 30 | 30 | 30 | 90 | 30 | 30 | 30 | 90 | 30 | 30 | 30 | 90 | 360
Stern, George - 1238 | [38 empty] | 9 | 22 | 5 | 36 | 2 |  |  | 2 |  |  |  |  | 38 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 160
Total | 13 | 36 | 113 | 162 | 89 | 49 | 20 | 158 | 8 | 28 | 53 | 89 | 82 | 126.5 | 29 | 237.5 | 646.5 | 16 | 177.5 | 151.5 | 345 | 94 | 50 | 43 | 187 | 68 | 134 | 121.5 | 323.5 | 102 | 122 | 32 | 256 | 1111.5 | 75 | 112 | 109 | 296 | 149.5 | 60 | 16 | 225.5 | 22 |  |  | 22 |  |  |  |  | 543.5 | 60 | 60 | 60 | 180 | 60 | 60 | 60 | 180 | 60 | 60 | 60 | 180 | 60 | 60 | 60 | 180 | 720
Total |  |  | 1 | 1 | 32.5 | 6 |  | 38.5 |  | 6.5 | 28 | 34.5 | 8 | 2.5 |  | 10.5 | 84.5 |  | 0.5 |  | 0.5 |  | 2 |  | 2 |  |  | 1 | 1 |  | 2 | 5.5 | 7.5 | 11 | 3.5 |  |  | 3.5 | 11 | 0.5 |  | 11.5 | [8 empty] | 15 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 13.3333 | 13.3333 | 13.3333 | 40 | 160
Paul roberts |  |  | 3 | 3 | [12 empty] | 3 |  |  |  |  | 48 | 28 | 1 | 77 |  |  | 13 | 13 |  | 1 |  | 1 | 91 | 7.5 | 6 | 5 | 18.5 | 10 | 4 |  | 14 | [8 empty] | 32.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
Total | [12 empty] | 2 |  |  | 2 | 2 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [42 empty] | 5 |  |  | 5 |  |  |  |  | 5 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 200
Total | 53 | 88 | 123 | 264 | 142 | 85 | 44 | 271 | 36 | 108 | 27 | 171 | 93 | 81 | 36 | 210 | 916 | 27 | 64 | 137 | 228 | 107 | 106 | 94 | 307 | 45 | 45 | 44 | 134 | 86 | 114 | 36 | 236 | 905 | 97 | 80 | 118 | 295 | 136 | 31.5 |  | 167.5 | [8 empty] | 462.5 | 26.6667 | 26.6667 | 26.6667 | 80 | 26.6667 | 26.6667 | 26.6667 | 80 | 26.6667 | 26.6667 | 26.6667 | 80 | 26.6667 | 26.6667 | 26.6667 | 80 | 320
Tucker, Justin - 0922 | [42 empty] | 5 |  |  | 5 |  |  |  |  | 5 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 200
Voigtlander, Johann - 1271 | [13 empty] | 76.5 |  | 76.5 | 76.5 |  | 155.5 | 121.5 | 277 | 72 | 24 | 38 | 134 | 51 | 121 | 96.5 | 268.5 | 69 | 61 | 16 | 146 | 825.5 | 46 | 82 | 70 | 198 | 68.5 | 13 | 3 | 84.5 | 8 |  |  | 8 |  |  |  |  | 290.5 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 16.6667 | 16.6667 | 16.6667 | 50 | 200
ENG-Electrical Engineer
ENG-Electrical Engineering Tech
ENG-Electrical Tech
ENG-Machinist
ENG-Mechanical Engineer
ENG-Mechanical Tech
Total | 66 | 124 | 240 | 430 | 263.5 | 140 | 64 | 467.5 | 44 | 142.5 | 108 | 294.5 | 185 | 210 | 65 | 460 | 1652 | 43 | 242 | 288.5 | 573.5 | 249 | 186 | 138 | 573 | 113 | 179 | 179.5 | 471.5 | 188 | 239 | 73.5 | 500.5 | 2118.5 | 183 | 198 | 232 | 613 | 306.5 | 96 | 16 | 418.5 | 27 |  |  | 27 |  |  |  |  | 1058.5 | 116.6667 | 116.6667 | 116.6667 | 350 | 116.6667 | 116.6667 | 116.6667 | 350 | 116.6667 | 116.6667 | 116.6667 | 350 | 116.6667 | 116.6667 | 116.6667 | 350 | 1440
Engineering
Total | 66 | 124 | 240 | 430 | 263.5 | 140 | 64 | 467.5 | 44 | 142.5 | 108 | 294.5 | 185 | 210 | 65 | 460 | 1652 | 43 | 242 | 288.5 | 573.5 | 249 | 186 | 138 | 573 | 113 | 179 | 179.5 | 471.5 | 188 | 239 | 73.5 | 500.5 | 2118.5 | 183 | 198 | 232 | 613 | 306.5 | 96 | 16 | 418.5 | 27 |  |  | 27 |  |  |  |  | 1058.5 | 116.6667 | 116.6667 | 116.6667 | 350 | 116.6667 | 116.6667 | 116.6667 | 350 | 116.6667 | 116.6667 | 116.6667 | 350 | 116.6667 | 116.6667 | 116.6667 | 350 | 1400
All
Notes:
Jul 9, 2025 12:40:38 PM PDT
Confidential Information. Do not distribute without permission.

## Sheet1
2026 Project Start Date: | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Total Resources[1] (in hours) for each resource category for all milestones listed here
MM/DD/2026
Milestone Date | 2025-02-26 | 2025-05-26 | 2025-06-26 | 2025-08-26 | All year
Milestone Description | Post-Arctic Maintenance | Power Upgrade Study | Thruster Design | Camera Upgrade | Program Management
Milestone Priority for 2026 | 2 | 3 | 1 | 4 | 5
(Rate 1-5)[2]
Electrical Engineer | 80 J.V. | 160 G. S. | 40 J.V. | 40 J.V. | 60 A. S. | 360 A. S. | 360
| 80 A. S. | 100 A. S. | 80 A. S. | 60 P. R. |  | 40 P. R. | 40
|  | 40 J.V. |  | 40 A.S. |  | 160 G. S. | 160
[6 empty] | 200 J.V. | 200
Software Eng-Embedded
Software Eng-Info Eng
Mechanical Engineer |  |  | 200 J. T. |  |  | 200 J. T. | 200
Mechanical Eng-Division
Mechanical Eng-Mfg
Associate Engineer
Electrical Tech | 40 J.M. | 40 J.M. | 40 J.M. | 40 J.M. |  | 160 J.M. | 160
Software Tech
Mechanical Tech | 100 F. F. | 40 F. F. | 100 F. F. | 40 F. F. | 40 F. F. | 320 F. F. | 320
[6 empty] | 0 | 1440
[1] This number should be the same number you entered on the web budget resource requests for this particular resource.
[2] E.g., enter a rating of 1 for highest priority, 5 for lowest priority.

## Information about this Sheet
Alana Sherman at Monterey Bay Aquarium Research Institute
Sheet | Labor Hours
Level | 902208 - Mini ROV Operations (Only)
Version | Budget 2026
Accounts | Labor Hours