## Sheet1
MINI ROV TO DO LIST (ELECTRICAL)
Owner | Description | Status | Priority (1 = high, 3 = low)
Dale | Test tilt |  | 2
Tom | install humidity sensor in epod |  | 1
Dale | fix "sci pt #2" button color on GUI |  | 3
Jim | Make up labels for epod and jboxes |  | 2
Dale | test hd camera comms |  | 3
Tom | install fan in epod |  | 1
Chad | mink dummies |  | 3
Chad | manip cable |  | 3
Alana | dvl cable |  | 3
Chad | Nano sea light cables |  | 2
Dale | Test sheave counter cable |  | 3
Dale | Make up new heading sensor can |  | 3
Tom | Make up new vicor housing cables |  | 1
Chad/Dale | Test vicor housing |  | 1
Chad | order spares for gfi |  | 3
Dale | help request for pc |  | 2
Chad | make up grounding clamp |  | 2
Tom | fix sci port serial wiring
Tom | frame gnd on vicors |  | 1
Jim | make up new ctd cable |  | 3
Chad | contros cable & test |  | 2
Chad | rewire and test gfi circuit |  | 2
Tom | Make up rattler power cable for epod |  | 1
Jim | Make up rotary oil filled cables |  | 1
| wire up rack gfi plate |  | 1