## Sheet1
2020 MiniROV Labor budget
Task | Sub task | Graves | Risi | Sherman | Flores | Marion | Parker | Macine shop
Focal Upgrade (free up fiber) |  | 80
| Topside |  |  | 20 |  | 20
| Subsea |  |  | 20 |  | 40 | 20
Thruster Upgrade
| Mechanical Design | 40 |  |  |  |  | 20
| Vicor can endcaps & rewire | 20 |  | 20 |  | 40 |  | 40
| New Jbox build | [6 empty] | 80
| Assembly & test | 60 |  | 20 | 80 | 40
Winch Upgrade
| Layout of new enclosure | 30
| Level wind software (auto) | 40
| Winch schematic |  |  | 20
| Hardware assembly & test | 20 |  |  | 40 | 20 | 20
Software Upgrade
| Combine various code modules | 120
| Add hooks for individual thruster control | 20 | 20
| Add config files | 20
| Training | 100 |  | 200
| Incorporate new Rock/Risi advanced nav code | 20 | 80
| Add error handling | 80
Documentation
| Clean up schematics and CAD files | 40 |  | 80
| Create maintenance proceedures | 80 |  | 80
| Assembly instructions for various sub assembies | 40
Maintenace
| Routine maintenance | 200 |  |  | 200 |  | 40 | 40
Totals |  | 1010 | 100 | 460 | 320 | 160 | 100 | 160