## Sheet1
Taiwan & Arctic cruise "To do list"
Item description |  | Priority | Assigned to
Swing Arm
| Fabricate new swing arm mount | 1 | Mike
| build up swing arm gear motor | 1 | Dale
| new software for swing arm |  | Dale
| tube cores | 1 | Mike
| quivers |  | Mike
| brackets for limit switches | 1 | Mike
| pot up limit switches & cable | 1 | Dale
| Make up swing arm cable | 1 | Dale
| Close up spare gear motor |  | Dale
| Pack spare swing arm parts |  | Dale
Van
| Make rack hold downs for new rack | 1 | Frank
| pack up van tools & spares |  | Dale
| Secure big screens | 1 | Frank
| add generator input to van breaker pannel |  | Dale
| Install winfrog/ranger rack in van | 1 | Dale
| Install video rack in van | 1 | Dale
| back up code on spare computer |  | Dale
| update software for ss pump on benthic sled. |  | Dale
| check in code for overlay on co-pilot |  | Dale
hook up video encoder/decoder
hook up aja deck/ethernet
| fix 16" monitor |  | Dale
sync project libraries
| hook up & test time server |  | Dale
| Add plug strip to wall |  | Dale
| load epos software on to raid drive |  | Dale
| install labview 2016 on main computer |  | Dale
| add logger output to winfrog & test |  | Dale
test AC/order new one if needed
| Order second video decoder |  | Dale
load epos on to co-pilot
fix camera 2
commit new code to svn
hook up winfrog computer on network
Vehicle mods/brackets
| Rewire DGH can for temp probe | 1 | Dale
| Rewire toolskid jbox for suction pump | 1 | Tom
| Mount suction pump on skid | 1 | Frank
| Mount DGH can on skid |  | Frank
| Mount DVL on skid |  | Frank
| paint front bumper foam | 2 | mike
| Design bracket for new beacon | 2 | Dale
trim vehicle
| design new suction tube for ss pump | 2 | Mike
| design new mount for suction tube | 2 | Mike
| drawings into shop for arctic temp can |  | Dale
| Install new sonar |  | Dale
| Comp and install j-box |  | Dale
| fix CT-2 software |  | Dale
| fix Temp probe software |  | Dale
mount drawer camera
| attach sled to ROV |  | Dale
Generator
| Change oil & filter in gen set | 2 | Frank
| test generator with van/rov/winch |  | Dale/Frank
| make weldable mounting plates for generator | 2 | Frank
Make up new van power cable
Winch
| cover for winch |  | Frank
| Camera bracket for winch level wind |  | MIke
| Install slip ring |  | Dale
| design adapter plate for new motor |  | dale
| order new flex hub |  | dale
order new hose for slip ring
| open up gear/motor opening in frame |  | frank mike
Spares
| pack up spare 24" monitors | 2 | Frank
| order video recorder | 2 | Dale
| build up spare thurster motor | 2 | Dale
| Gather up bird water samplers | 2 | Frank
| grab spares swing arm motor from midwater skid |  | Dale
| grab spare comps off of midwater skid |  | Frank
| Test gas sampler solenoid valve | 1 | Dale
| inventory of spare cables |  | Alana
| create back up for co-pilot computer |  | Dale