2014 MBA/MBARI

Exhibit Project

Projected Tasks

- Support/Animation Structure

  - Suspension Framework

    - Building Interface

  - Rotation Framework

    - Bearing(s)

    - Drive Mechanism

      - Rate: 1 rev./Minute

    - Control hardware/Software

    - Electrical

    - Other

  - Tilt/Lifting Mechanism(s)

    - Bearings

    - Drive Mechanism(s)

      - Lifting Rate: 1 inch/Second

    - Rollers

    - Other

  - Drape/Camouflage

- ROV

  - Structure

    - Scaling

      - Material

      - Weight Limit ~ 150 #

  - Foam Pack

    - Scaling

    - Material

      - Weight Limit ~ 25#

    - Art Work

      - Color

      - Decal

      - Other

  - Accessory Mock-ups

    - Scaling

    - Thrusters

    - Lights

    - Cameras

    - Instrumentation

    - Manipulator

    - Cables and Tubing

    - Other

Timeline:

16April2014

- Preliminary Design Review

  - Design Concepts

  - Technical Issues

  - Exhibit interfaces

    - Suspension Framework

      - Building Interface

        - Structure

    - Animation Platform

      - Electrical

      - Slip Rings

    - Scaled ROV Model

      - Frame

      - Foam Pack

      - Ancillary Equipment

      - Thrusters

        - Actuation Motors

      - Sensors

    - Update on MBA exhibit space and film

18June2014

- Critical Design Review

  - Detailed Design

  - Project Progress

  - Risk Management

    - Suspension Framework

    - Animation Platform

      - Drive and lift Mechanisms

        - Electrical and electronics

    - ROV Model

      - Fabrication

      - Assembly

      - Final Weight

    - Update on MBA Exhibit

      - Final Layout

        - Entrance and Exit

        - Console

        - Screen

        - Projectors

01August2014

- Final Design Review

  - Component Testing and Interfacing

    - Suspension Framework and Animation Platform

    - Fully Assembled Scale Model ROV

29August2014

- Delivery to MBA of Animated ROV Assembly