Estimated Work Breakdown for

MBA/MBARI Exhibit Design 2014

Farley F. Shane

ROV Suspension Structure (Estimated Fab Time: 22 hrs)

- Mechanical Design for Lifting/Tilt and Pan Mechanism	24 hours

- Welded Aluminum Vertical Suspension Post 	3 hours (Est.Mat’ls $100) (2 hrs)

  - 3 drawings

    - Post

    - Bearing baseplate

    - Integrated assembly/Weld Spec

- Acetal Support Bushing 		10 hours (Est. Mat’ls $300) (4 hrs)

  - 4 drawings

    - Split Bushings (Right and Left)

    - Baseplate

    - Integrated assembly

- Aluminum ROV Panning and Support Plate	24 hours (Est.Mat’ls $500) (8 hrs)

  - 2 drawings

    - Panning and Support Plate Details

      - Line Rollers integration

      - Lift Motors Placement

      - Pan Motor Placement

      - Pan Gear integration

- ROV lift Motor (3ea.) Base 	8 hours (Est. Matl’s $100) (4 hrs)

  - 1 drawing

- Lift Motor Spool Integration/Support 	4 hours (Est. Mat’ls $300)

  - 1 drawing

- ROV Pan Motor Base	24 hours (Est. Mat’ls $300) (4 hrs)

  - 3 drawings

    - Vertical Suspension Post Interface Base

    - Pan Motor Foundation

    - Integrated assembly drawing

- Assembly Drawing with Bill of Materials		4 hours

- Possible Additional Drawings	8 hours (Est. Mat’ls $300)

  - (Cable management, strain reliefs, ancillary support, etc.)

Total estimate to design  ROV Support Structure = 109 hours

Fabrication and Materials Costs are extra.

Estimate for equipment:

4 ea. Lift/Pan Gear Motors with encoders @ $800 ea. = $3200

3 ea. Line spool assemblies @ $100 ea. = $300

3 ea. Rollers for lift lines @ $20 ea. = $60

4 ea. Servo-amplifiers @ $300 ea. = $1200

1 ea. Thrust Bearing @ $100 ea. = $100

Fasteners = $100

NOTE:  ADDITIONAL STRUCTURAL DESIGN ELEMENTS WILL BE REQUIRED TO SECURELY INTEGRATE THE ROV SUSPENSION STRUCTURE INTO THE BUILDING STRUCTURE. THESE ITEMS ARE NOT A PART OF THIS ESTIMATE.  ADDITIONAL HOURS (TBD) ARE NECESSARY FOR AN ELECTRICAL ENGINEER TO CONSULT ON AN APPROPRIATE GEARMOTOR/ENCODER AND ANCILLARY INSTRUMENTATION.

Scale Model of ROV Doc Ricketts (Estimated Fab Time: 52 hrs)

- Prepare scale model dimensional drawings of vehicle for fabrication

  - Flotation Pack		32 hours  (Guess-timation  $1000) (12 hrs)

    - 3 sheets

  - Frame		50 hours	(Est. Mat’ls = ~100ft. of tubing @ $10.50/ft. = $1050)

    - 8 sheets including assembly drawing		(40 hrs)

- Working with Fabricator to make model		8 hours

Additional Materials for mock-ups of vehicle components (Est. $1000)

Total estimate to design  scale model of ROV Doc Ricketts = 90 hours

Total estimated fabrication time for Support/Animation Structure and Scaled ROV = 74 hours