## Dome testing
Cost estimate
Modified domes | 2700
Customs and freight charges from China | 300
Mitutoyo linear gauge readout | 800 | Can find much cheaper suitable unit on ebay
Microphone | 200 | May be cheaper
thermistor | 50
Material for dummy cap and sensor mount | 500
waterproof connectors and cable | 200 | We probably have something in house
Estimate of pressure test cost | 3000 | wild guess. DSPL, Pen State are likely canditates. There is the possibility of doing the test at port hueneme for free
Shipping cost | 200
Travel cost | 500 | travel may not be required if pressure test facility has good tech who can setup and supervise the test
Labor estimate
Machine shop time for dummy cap and sensors mounts | 4 days
EE time for data logging setup | 2 days | might be more, check with Mark
ME time for FEA | 5 days
ME time for test parts design and order | 3 days
ME time for test preparation (preparation of components, assembly) | 3 days
ME time for pressure test (coordination with pressure test facility, travel, test supervision) | 2 days
ME time for overhead (research, purchasing, coordination, documentation etc) | 2 days

## Flotation
Cost estimate
Materials (glue, tools) | 200
Labor estimate
ME tech time | 3 days | Machining of syntactic blocks
ME time (Francois) | 3 days | Includes design, ordering, disassembly of I2map nose, modification of cable routes, reassembly and test in the tank
Estimate of cost in case we must have it made by outside vendor | 1500