## Sheet1
Kelp Forest Array - Central Node GF Troubleshooting
| Who | Time
Terminate 2m whip with 2nd SeaConn connector | ET | 2 days
Terminate 15m whip with SeaConn connector | ET | 2 days
Test CN & 15 meter whip in test tank | Chad/Jim | 3 days
Kelp Forest Array - Micronode
| Who | Time
Design new endcap | Farley | 2 days
Fabricate new endcap | Mach | 1 week
Populate endcap with 2 SeaConn connectors | ET | 1 day
Prewire the connectors | ET | 1 day
swFOCE - Micronode Whip
| Who | Time
Order 30 meter section of cable | Chad | ?
Terminate/pot both ends of cable | ET | 2 days
Kelp Forest Array - Redeployment
| Who | Time
quikFOCE - Housing
| Who | Time
Design MINL to MINK adaptors | Farley | 1 day
Fabricate adaptors | Mach | 2 days
Install adaptors/wire housing | ET | 1 week
quikFOCE - Whips
| Who | Time
Design Whips | Chad | 2 days
Wire Whips | ET | 1 day
Test Whips | Chad | 2 days
Pot Whips | ET | 2 days
quikFOCE - Integration/Testing
| Who | Time
Assemble/attach all pieces | Chad | 1 day
Bench test functionality of all instruments (HW + SW) | Chad/SE | 1 week
Test tank testing (Ops + GF) | Chad | 1 week