quikFOCE Tasks

Chad Kecy

03-27-2014

quikFOCE - Electronics Housing

We are reusing the D-Conn can from the dpFOCE CO2 system for use with this experiment. I was able to find used and spare parts for this housing. The internal framing is being used as well. The adaptors have been fabricated but they do not fit into the endcap – they are being redesigned and/or reworked.

|  | Who | Time |
| --- | --- | --- |
| Design MINL to MINK adaptors | Farley | 1 day |
| Fabricate adaptors | Mach | 2 days |
| Install adaptors/wire housing | ET | 1 week |

quikFOCE - Whips

These are two Y-whips: one for pH+CTD and pH+Thruster. The whips are already wired, i am waiting on the housing to be wired to test them.

|  | Who | Time |
| --- | --- | --- |
| Design Whips | Chad | 2 days |
| Wire Whips | ET | 1 day |
| Test Whips | Chad | 2 days |
| Pot Whips | ET | 2 days |

quikFOCE – Integration and Testing

I will be performing standard integration testing. I’m guessing Bob will be providing the software support on this aspect of FOCE. We will drop it to the bottom of the tank and include GF testing.

|  | Who | Time |
| --- | --- | --- |
| Assemble/attach all pieces | Chad | 1 day |
| Bench test functionality of all instruments (HW + SW) | Chad/SE | 1 week |
| Test tank testing (Ops + GF) | Chad | 1 week |

quikFOCE – Deployment

The KFA will have been redeployed by this point. The deployment will consist of the use of the R/V Paragon and divers. The divers will bring the 30 meter section of whip to the Paragon. We will make the connection dry and send the experiment back down. The whips and all instruments will be attached to the housing (all dry connectors).

The actual logistics of deploying quikFOCE and attached instruments to the chamber need to be worked out. Peter W. has some ideas.