## Sheet1
|  | Time | Difficulty | Notes
(work days)
Central Node (x1) |  | 15
MV Conv Bd |  | 12 |  | Sub tasks in italics
Board Fabrication | Outside | 5 |  | In progress
Parts Population | E-Tech | 2
Initial Electrical Testing | Chad | 1
Initial Software Testing | Bob | 2
Install into Central Node | E-Tech | 2
Central Node Standalone Testing | Bob/Chad | 3
Gateway Node (x2) |  | 11
Manufacture Housings | Farley/M-Shop | 3 |  | 1/2 built; 4 week back log in shop
Assemble Housings | Farley | 1
Housing Wiring | E-Tech | 2
Initial Electrical Testing | Chad | 2
Gateway Node Standalone Testing | Kent/Chad | 3
Main Electronics Housing (x2) |  | 0
Ready for integration testing |  | 0
Sensor Node (x8) |  | 8
Sensor Node Housing Wiring | E-Tech | 2 |  | 5/8 complete; Housings on backorder
Pressure Testing of Test SN | Chad/Jim | 5 |  | In progress
Pot the Housings | Jim/Chad | 1 |  | Will do all 8 at one time
Valve Box (x2) |  | 9
Manufacture Housings | Farley | 3 |  | Drawings submitted; 4 week back log in shop
Housing Wiring | E-Tech | 2
Initial Electrical Testing | Chad | 2
Valve Box Standalone Testing | Kent/Chad | 2
Camera (x2) |  | 5
Manufacture Housings | Farley/M-Shop | 3 |  | Still designing
Housing Wiring | E-Tech | 1
Initial Electrical Testing | Chad | 1
Instruments (many, 12-14) |  | 7
Gather Instruments/whips | Chris L/Chad | 1
Drawings for custom whips | Chad | 1
Fabricate custom whips | E-Tech | 3
Test individual whips | Chad/Kent/Chris L | 2
| Total | 55

## Sheet2
| Qty/Frame | Frames | Total
SBE18S | 3 | 2 | 6
SBE52S | 2 | 2 | 4
Satlantic PAR | 2 | 2 | 4
Omega Fmeter | 1 | 2 | 2
Valve Box | 1 | 2 | 2
SBE xx Pump | 1 | 2 | 2
20