## Sheet1
| EE | ME | SE | ET | MT
Interconnection Cables (20+)
Wire connectors |  |  |  | 20
Pot cables |  |  |  |  | 40
Central Node (x1, x1)
Design Front End Elec | 16
Test Front End | 8 |  | 8
Test Central Node | 8 |  | 8
Have MV board fabricated
Design Front End Housing |  | 32
Wire Front End |  |  |  | 16
Wire Central Node |  |  |  | 16
Populate MV board |  |  |  | 8
Test MV board | 8 |  | 8
Build housing & endcaps |  |  |  |  | 32
Main Elec Housing (x2)
Build housing & endcaps |  |  |  |  | 32
Wire MEH |  |  |  | 16
Test MEHs | 8 |  | 8
Gateway Node (x2)
Have pcbs fabricated | 4
Populate pcbs |  |  |  | 16
Test Board stack | 16
Wire housing |  |  |  | 32
Build housing & endcaps |  |  |  |  | 32
Test Gateway Nodes | 32 |  | 32
Sensor Nodes (x8)
Have pcbs fabricated | 4
Populate pcbs |  |  |  | 16
Test boards | 16
Wire sensor nodes |  |  |  | 64
Test the Sensor Nodes | 32 |  | 32
Pot the SN Housings |  |  |  |  | 40
Valve Box (x2)
Have pcb fabricated | 4
Populate pcb |  |  |  | 8
Wire housing |  |  |  | 16
Build housing |  |  |  |  | 16
Test valve box | 8 |  | 8
Camera Housing (x2)
Build housings |  |  |  |  | 16
Wire housings |  |  |  | 16
Test camera | 8 |  | 8
Thrusters (x2)
Build thruster mechanisms |  |  |  |  | 32
Test thrusters | 8 |  | 8
System Level
Integration testing | 80 |  | 80
Frames
Build swFOCE frames |  |  |  |  | 40
Integrate ducting onto frames |  |  |  |  | 24
Total labor by discipline | 260 | 32 | 200 | 244 | 304