## Sheet1
Central Node (x1) | Who | Status
Rewire new bulkhead connectors | Jim M | Done
Reassemble the internal electronics | Jim M | In Progress
Test Central Node electronics | Chad
Main Electronics Housing (x2) | Who | Status
Rewire new bulkhead connectors | Jim M | In Progress
Reassemble the internal electronics | Jim M
Test MEH electronics | Chad
Software Testing | Bob | In Progress
Gateway Node (x2) | Who | Status
Populate 2 Vicor Mini boards | ET Shop
Mechanical housing design | Farley
Wire the internal electronics | Jim M
Test the GN electronics | Chad
Software testing | Kent
Sensor Node (x8) | Who | Status
Final configuration of SN boards | Chad | Done
GN to SN Software Testing | Kent/Bob
Package in project box | Chad/Jim S | In Progress
Connect whips | Jim M
Pot the housings | Jim S
Valve Box | Who | Status
Fab/populate current loop transceiver | Jose | In Progress
Test current loop transceiver | Chad
Mechanical housing design | Farley
Wire internal electronics | Jim M
Test electronics | Chad
Software testing | Kent
Camera | Who | Status
Mechanical housing design | Farley
Wire internal electronics | Jim M
Test camera | Chad