swFOCE Repair Work Sept 2015

Cable Terminations
Terminate both ends of the (2) new 30m cables with MINK16-CCP connectors
Test both 30m cables using existing quikFOCE can
Pot all four ends of the (2) 30m cables

Prior to Sept 10th Cruise
x - Verify George has all of the Subconn dummies he needs for housings recovery
Sept 10th
R/V Paragon – Recover 15m cables (2) and 52m cable
Bring Jose along
Dummy off bulkhead connections (5) 
	CN (3)	
	MEH #1 (1)
	MEH #2 (1)
Post Sept 10th Cruise
Re-Terminate the bad end of the 52m cable
Test 52m cable
Pot new connector on 52m cable

KFA Power Can
Once the (2) 30m cables and (1) 52m cable have been tested,
Remove all of the electronics from the quikFOCE can
Install 300Vdc:12Vdc Micro Vicor
Use existing J-Box cable from dpFOCE
Test Power Can (loaded condition)

Motors
Fabricate (2) Y-Whips (use for testing)
Test Elmo+motor on bench
Test Elmo+motor on bench with Sensor Node
Test Elmo+motor on bench with Sensor Node and Gateway Node
Fabricate oil filled cabling assembly (utilizing the 2 Y-whips)
Test entire cable+Elmo+motor dry
Test entire cable+Elmo+motor in the test tank

Second Deployment (Last Half of Sept)
Deploy (2) 30m and (1) 52m cables
Install KFA Power Can on Micronode
Test power/communications from shore while housings are on the R/V Paragon
Deploy new motor assemblies the same day?

September 2015

Sun		Mon		Tue		Wed		Thur		Fri		Sat
	30
	31
	1
	2
	3
	4
Off Friday
	5

	6
	7
Labor Day
	8
	9
	10
R/V Paragon
	11
	12

	13
	14
	15
	16
	17
Chad OffShore
	18
Off Friday
Chad OffShore
	19
Chad OffShore

	20
Chad OffShore
	21
Chad OffShore
	22
Chad OffShore
	23
Chad OffShore
	24
Chad OffShore
	25
Chad OffShore
	26
Chad OffShore

	27
Chad OffShore
	28
Chad OffShore
	29
Chad OffShore
	30
Chad OffShore
	[bookmark: _GoBack]
	
	




